## Items
ID | Kind | Level | Type | Summary | State | Owners | Created Date | Planned Start Date | Planned Completion Date | Team | Work Items | Work Item For | Spawns | Spawned By | Closed Date | Review Owners Ref | Planned Prepared Date | Review Planned Start Date Ref | Review Planned Completion Date Ref | Review Cycle Count | Project | Defined State Duration | Planned State Duration | Started State Duration | Implemented State Duration | Prepared State Duration | Overdue Planned Completion Date | Overdue First Build Date | Affected Objects | Planned Effort | First Build Date | Remaining Effort | Change Request For | Rollup Actual Effort | Rollup Planned Effort | Rough Effort Estimation | Classification | Maturity Level | Target Date | Analysis Target Date | Analysers | Action For | Actions
10829998 | ecr |  | ALM_Change Request | JAC_X2441_[ECR] Update Vehicle Fault Matrix | ALM_Closed | Li Jiajun GNG CDAY211 (Z0156047) | 2026-07-02 13:54 |  |  | (9824520) AP-EPM-Engineering Project Manager PR65978 | 10760094, 10839913, 10839948, 10727066, 10768580, 10768660, 10768670, 10768560, 10727258, 10727263, 10727294, 10727296, 10727298, 10751229, 10745256, 10745259, 10745261, 10745263, 10745265, 10745267, 10751235, 10751244 | 10725430 |  |  | 2026-09-09 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 25.765 | 1.00805555555556 | 74.1641666666667 | [5 empty] | 0 |  | 0 |  | 265.05 | 73 |  | Requirements |  |  | 2026-05-20 | Xu Huiling GNG CDAY212 (Z0129466), Gu Guangyu SGH CDAY211 (Z0235949) |  | 10849908, 10849913, 10931228
10798652 | ecr |  | ALM_Change Request | JAC_X2441_[ECR] Update Debounce Time When Switching between Vehicle Control and 4th Lane Control | ALM_Closed | Li Jiajun GNG CDAY211 (Z0156047) | 2026-06-18 13:03 |  |  | (9824520) AP-EPM-Engineering Project Manager PR65978 | 10829683, 10874514, 10854586, 10867714, 10819491, 10819493, 10849388, 10819497, 10829308, 10829364, 10829366 | 10725430 |  |  | 2026-09-17 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 311.537222222222 | 162.593611111111 | 991.127222222222 | [5 empty] | 0 |  | 0 |  | 83.5 | 23 |  | Requirements |  |  | 2026-02-10 | Xu Huiling GNG CDAY212 (Z0129466), Liao Jiaxin SGH CDAW11 (Z0283131) |  | 10848071, 10848072, 10931221
10772898 | ecr |  | ALM_Change Request | ECR for AES128 algorithm to be implemented for EM2EU (For some of China markets) | ALM_Analysed | Jagathpally Varsha HYD CDAIY (Z0197167) | 2026-06-08 18:40 |  |  | (6418984) TV-TAV-TestAndValidation PR60806 | 10408346, 10408352, 10408335, 10408339 | 6565461 | [8 empty] | /Steering/Projects/BYD/EM2E_CD_EPS/PR60806_ADS_APP_MY2022_BYD EM2E_EPS_CD | 0.0211111111111111 | [7 empty] | 0 |  | 0 |  | 79 | 77 |  | Documentation |  |  |  | Jagathpally Varsha HYD CDAIY (Z0197167), Tummuri Sahitya HYD CDAIW1 (Z637049)
10629051 | ecr |  | ALM_Change Request | JAC_Huawei_X2411_[ECR] Update CAN Matrix for X6M | ALM_Closed | Wu Zhuxia SGH CDAW13 (Z0171653) | 2026-04-02 17:48 |  |  | (9824520) AP-EPM-Engineering Project Manager PR65978 | 10672607, 10683917, 10807059, 10637012 |  |  |  | 2026-07-16 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 140.198055555556 | 0.00138888888888889 | 2.87277777777778 | [5 empty] | 0 |  | 0 |  | 52.7 | 40 |  | Requirements |  |  | 2026-02-05 | Li Jiajun GNG CDAY211 (Z0156047), Gu Guangyu SGH CDAY211 (Z0235949) |  | 10639636, 10639637
10624439 | ecr |  | ALM_Change Request | [Improvement][ECR][AutoX ModelM]Changes of Mode B & FMM | ALM_Started | Zhu Yongwei GNG CDAY211 (Z0138244), Jiang Wen EXT Alten (Z0273663) | 2026-04-01 11:09 |  |  | (8667826) AP-EPS-Systems Lead - LSE PR63909 | 10663321, 10692965, 10713695, 10709808, 10830539, 10798664, 10798733, 10799943, 10807784, 10808100, 10808128, 10707491, 10609499, 10617043, 10643329, 10720486, 10546386, 10546388, 10992974, 10992979, 10992984, 10992988, 10993028, 10993034, 10993038, 10993046, 10993048, 10993050, 10993052, 10993054, 10993057 | 10445607 | [8 empty] | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 21.6716666666667 | 0.0025 | 3622.67277777778 | [5 empty] | 0 |  | 0 |  | 239.3 | 943 |  | Requirements |  |  | 2026-08-31 | Chen Ting EXT Alten (Z0099343), Wang Lemin GNG CDAY622 (Z0138417), He Zhaoxia GNG CDAY212 (Z0151154), Guo Haiwen GNG CDAY622 (Z0163467) |  | 10624464
10506032 | ecr |  | ALM_Change Request | JAC_X2441_[ECR] Add Lane1 Sensor SENT Signal External Connection from Both HWA and FAA for X6U | ALM_Closed | Tan Hong SGH CDAH5 (TanH4), Li Jiajun GNG CDAY211 (Z0156047) | 2026-02-03 09:34 |  |  | (9824520) AP-EPM-Engineering Project Manager PR65978 | 10637699, 10808043 | 10725430 |  |  | 2026-09-17 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 331.21 | 0.0144444444444444 | 1276.33 | [5 empty] | 0 |  | 0 |  | 12 | 8 |  | Requirements |  |  | 2026-03-27 | Tan Hong SGH CDAH5 (TanH4), Li Jiajun GNG CDAY211 (Z0156047), Gu Guangyu SGH CDAY211 (Z0235949) |  | 10569939, 10569943, 10569945, 10931218
10446618 | ecr |  | ALM_Change Request | JAC_Huawei_X2411_[ECR] Update Fault Matrix | ALM_Closed | Li Jiajun GNG CDAY211 (Z0156047) | 2026-01-06 17:35 |  |  | (9824533) AP-EPS-Systems Lead - LSE PR65978 | 10496999, 10570063, 10570075, 10520078, 10450157, 10477476, 10428407, 10428438, 10428448, 10428488, 10468010, 10512985 |  |  |  | 2026-05-14 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.3372222222222222 | 28.2791666666667 | 1132.205 | [5 empty] | 0 |  | 0 |  | 157 | 87 |  | Requirements |  |  | 2026-01-16 | Li Jiajun GNG CDAY211 (Z0156047), Wu Zhuxia SGH CDAW13 (Z0171653), Wang Alex SGH CDAY52 (Z0218623), Gu Guangyu SGH CDAY211 (Z0235949) |  | 10465820, 10465824
10436107 | ecr |  | ALM_Change Request | JAC_X2441_[ECR] Update Vehicle L4 Architecture for X6U | ALM_Closed | Ran Zhenguo SGH CDAW13 (RanZ), Li Jiajun GNG CDAY211 (Z0156047) | 2025-12-24 15:45 |  |  | (9824520) AP-EPM-Engineering Project Manager PR65978 | 10576191, 10637012, 10637699, 10739988, 10808043, 10860839 | 10725430 |  |  | 2026-07-22 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.0355555555555556 | 0.00194444444444444 | 3.83277777777778 | [5 empty] | 0 |  | 0 |  | 227 | 212 |  | Requirements |  |  | 2026-02-13 | Ran Zhenguo SGH CDAW13 (RanZ), Wang Alex SGH CDAY52 (Z0218623), Gu Guangyu SGH CDAY211 (Z0235949) |  | 10512233, 10512237
9965134 | ecr |  | ALM_Change Request | [Customer][ECR][AutoX ModelM] PV Mechanical change | ALM_Realized | Geng Zhiwei SGH CDAE15 (Z0223934), Jiang Wen EXT Alten (Z0273663) | 2025-06-05 16:06 |  |  | (8667814) AP-EPM-Engineering Project Manager PR63909 | 10272597, 10827208, 10830568, 10830592, 10272583 | 9384136 | [8 empty] | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 4631.73638888889 | 0.005 | 4200.79083333333 | [5 empty] | 0 |  | 0 |  | 77.5 | 33 |  | Requirements |  |  | 2026-01-23 | Xie Haoting SGH CDAH212 (XieH), Xu Shun SGH CDAH24 (XuS21), Zhu Yongwei GNG CDAY211 (Z0138244) |  | 10418469, 10418539, 10418545, 10418573
8555340 | ecr |  | ALM_Change Request | [Customer] [ECR] [NIO NPD] New vehicle speed signals | ALM_Closed | Li Jiajun GNG CDAY211 (Z0156047) | 2023-12-20 17:14 |  |  | (6522739) AP-EPM-Engineering Project Manager PR60577 | 8139278, 8962576, 8962909, 8963004, 9055364 | 8085717 |  |  | 2024-06-21 | [5 empty] | /Steering/Projects/NIO/NPD/PR60577_ADS_APP_MY2025_NIO_NPD_SbW_AP | 3377.649722222222 | 54.16944444444444 | 161.7413888888889 | [5 empty] | 0 | 2024-05-30 | 0 |  | 100 | 410 |  | Requirements |  |  | 2024-01-11 | Ran Zhenguo SGH CDAW13 (RanZ), Xie Meng EXT Alten (Z0136558) |  | 8555350, 8555359, 9047930
10993057 | work_item | 0 | ALM_Task | AutoX_Sbw_P¦SYST_Build_AutoX_SBW_P_RL3¦Sys.4-5¦Full regression test¦¦Test Execution¦L0_Sbw Voltage Protection(GB00) | ALM_Planned | Xiu Zhenhong GNG CDAY55 (Z0199168) | 2026-09-30 12:54 | 2026-08-17 | 2026-08-24 | (8667835) MS-SYS-SystemTesting PR63909 |  | 10624439, 10992968 |  |  |  | Xie Yilin SGH CDAY55 (Z0151165) | 2026-08-21 |  |  |  | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | [5 empty] | 1900-02-06 |  | Qualification Test | 30 |  | 30
10993054 | work_item | 0 | ALM_Task | AutoX_Sbw_P¦SYST_Build_AutoX_SBW_P_RL3¦Sys.4-5¦Full regression test¦¦Test Execution¦L1_FAA Excessive Friction Detection(GB00) | ALM_Planned | Xiu Zhenhong GNG CDAY55 (Z0199168) | 2026-09-30 12:51 | 2026-08-17 | 2026-08-24 | (8667835) MS-SYS-SystemTesting PR63909 |  | 10624439, 10992968 |  |  |  | Xie Yilin SGH CDAY55 (Z0151165) | 2026-08-21 |  |  |  | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | [5 empty] | 1900-02-06 |  | Qualification Test | 30 |  | 30
10993052 | work_item | 0 | ALM_Task | AutoX_Sbw_P¦SYST_Build_AutoX_SBW_P_RL3¦Sys.4-5¦Full regression test¦¦Test Execution¦L1_FAA Overuse Protection(GB00) | ALM_Planned | Xiu Zhenhong GNG CDAY55 (Z0199168) | 2026-09-30 12:49 | 2026-08-17 | 2026-08-24 | (8667835) MS-SYS-SystemTesting PR63909 |  | 10624439, 10992968 |  |  |  | Xie Yilin SGH CDAY55 (Z0151165) | 2026-08-21 |  |  |  | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | [5 empty] | 1900-02-06 |  | Qualification Test | 30 |  | 30
10993050 | work_item | 0 | ALM_Task | AutoX_Sbw_P¦SYST_Build_AutoX_SBW_P_RL3¦Sys.4-5¦Full regression test¦¦Test Execution¦L1_FAA Straight Ahead Learning(GB00) | ALM_Planned | Xiu Zhenhong GNG CDAY55 (Z0199168) | 2026-09-30 12:47 | 2026-08-17 | 2026-08-24 | (8667835) MS-SYS-SystemTesting PR63909 |  | 10624439, 10992968 |  |  |  | Xie Yilin SGH CDAY55 (Z0151165) | 2026-08-21 |  |  |  | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | [5 empty] | 1900-02-06 |  | Qualification Test | 20 |  | 20
10993048 | work_item | 0 | ALM_Task | AutoX_Sbw_P¦SYST_Build_AutoX_SBW_P_RL3¦Sys.4-5¦Full regression test¦¦Test Execution¦L1_FAA End Stop Protection(GB00) | ALM_Planned | Xiu Zhenhong GNG CDAY55 (Z0199168) | 2026-09-30 12:44 | 2026-08-17 | 2026-08-24 | (8667835) MS-SYS-SystemTesting PR63909 |  | 10624439, 10992968 |  |  |  | Xie Yilin SGH CDAY55 (Z0151165) | 2026-08-21 |  |  |  | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | [5 empty] | 1900-02-06 |  | Qualification Test | 30 |  | 30
10993046 | work_item | 0 | ALM_Task | AutoX_Sbw_P¦SYST_Build_AutoX_SBW_P_RL3¦Sys.4-5¦Full regression test¦¦Test Execution¦L1_FAA Manual Driving Support (Angle Path)(GB00) | ALM_Planned | Xiu Zhenhong GNG CDAY55 (Z0199168) | 2026-09-30 12:41 | 2026-08-17 | 2026-08-24 | (8667835) MS-SYS-SystemTesting PR63909 |  | 10624439, 10992968 |  |  |  | Xie Yilin SGH CDAY55 (Z0151165) | 2026-08-21 |  |  |  | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | [5 empty] | 1900-02-06 |  | Qualification Test | 20 |  | 20
10993038 | work_item | 0 | ALM_Task | AutoX_Sbw_P¦SYST_Build_AutoX_SBW_P_RL3¦Sys.4-5¦Full regression test¦¦Test Execution¦L1_HWA-Haptic Driver Notification-(GB00) | ALM_Planned | Xie Yilin SGH CDAY55 (Z0151165) | 2026-09-30 12:28 | 2026-08-17 | 2026-08-24 | (8667835) MS-SYS-SystemTesting PR63909 |  | 10624439, 10992968 |  |  |  | Xiu Zhenhong GNG CDAY55 (Z0199168) | 2026-08-21 |  |  |  | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | [5 empty] | 1900-02-06 |  | Qualification Test | 30 |  | 30
10993034 | work_item | 0 | ALM_Task | AutoX_Sbw_P¦SYST_Build_AutoX_SBW_P_RL3¦Sys.4-5¦Full regression test¦¦Test Execution¦L1_HWA-Virtual End Stop-(GB00) | ALM_Planned | Xie Yilin SGH CDAY55 (Z0151165) | 2026-09-30 12:25 | 2026-08-17 | 2026-08-24 | (8667835) MS-SYS-SystemTesting PR63909 |  | 10624439, 10992968 |  |  |  | Xiu Zhenhong GNG CDAY55 (Z0199168) | 2026-08-21 |  |  |  | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | [5 empty] | 1900-02-06 |  | Qualification Test | 30 |  | 30
10993028 | work_item | 0 | ALM_Task | AutoX_Sbw_P¦SYST_Build_AutoX_SBW_P_RL3¦Sys.4-5¦Full regression test¦¦Test Execution¦L1_HWA-Straight Ahead Learning-(GB00) | ALM_Planned | Xie Yilin SGH CDAY55 (Z0151165) | 2026-09-30 12:22 | 2026-08-17 | 2026-08-24 | (8667835) MS-SYS-SystemTesting PR63909 |  | 10624439, 10992968 |  |  |  | Xiu Zhenhong GNG CDAY55 (Z0199168) | 2026-08-21 |  |  |  | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | [5 empty] | 1900-02-06 |  | Qualification Test | 30 |  | 30
10992988 | work_item | 0 | ALM_Task | AutoX_Sbw_P¦SYST_Build_AutoX_SBW_P_RL3¦Sys.4-5¦Full regression test¦¦Test Execution¦L1_HWA-Variable Steering Ratio-(GB00) | ALM_Planned | Xie Yilin SGH CDAY55 (Z0151165) | 2026-09-30 11:31 | 2026-08-17 | 2026-08-24 | (8667835) MS-SYS-SystemTesting PR63909 |  | 10624439, 10992968 |  |  |  | Xiu Zhenhong GNG CDAY55 (Z0199168) | 2026-08-21 |  |  |  | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | [5 empty] | 1900-02-06 |  | Qualification Test | 30 |  | 30
10992984 | work_item | 0 | ALM_Task | AutoX_Sbw_P¦SYST_Build_AutoX_SBW_P_RL3¦Sys.4-5¦Full regression test¦¦Test Execution¦L1_HWA-Manual Driving Support (Torque Path)-(GB00) | ALM_Planned | Xie Yilin SGH CDAY55 (Z0151165) | 2026-09-30 11:29 | 2026-08-17 | 2026-08-24 | (8667835) MS-SYS-SystemTesting PR63909 |  | 10624439, 10992968 |  |  |  | Xiu Zhenhong GNG CDAY55 (Z0199168) | 2026-08-21 |  |  |  | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | [5 empty] | 1900-02-06 |  | Qualification Test | 30 |  | 30
10992979 | work_item | 0 | ALM_Task | AutoX_Sbw_P¦SYST_Build_AutoX_SBW_P_RL3¦Sys.4-5¦Full regression test¦¦Test Execution¦L1_HWA-MDS Angle Path-(GB00) | ALM_Planned | Xie Yilin SGH CDAY55 (Z0151165) | 2026-09-30 11:25 | 2026-08-17 | 2026-08-24 | (8667835) MS-SYS-SystemTesting PR63909 |  | 10624439, 10992968 |  |  |  | Xiu Zhenhong GNG CDAY55 (Z0199168) | 2026-08-21 |  |  |  | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | [5 empty] | 1900-02-06 |  | Qualification Test | 30 |  | 30
10992974 | work_item | 0 | ALM_Task | AutoX_Sbw_P¦SYST_Build_AutoX_SBW_P_RL3¦Sys.4-5¦Full regression test¦¦Test Execution¦L1_HWA-Handwheel Damping(GB00) | ALM_Planned | Xie Yilin SGH CDAY55 (Z0151165) | 2026-09-30 11:21 | 2026-08-17 | 2026-09-28 | (8667835) MS-SYS-SystemTesting PR63909 |  | 10624439, 10992968 |  |  |  | Xiu Zhenhong GNG CDAY55 (Z0199168) | 2026-08-21 |  |  |  | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | [5 empty] | 1900-01-02 |  | Qualification Test | 30 |  | 30
10874514 | work_item | 0 | ALM_Task | JAC_X2441_SbW ¦ OTS2_SW_RL2_RC2 ¦ SWE.5&6 ¦ New and Changed Requirements ¦ Software test ¦ Software Test Management ¦ Software Test Summary Report | ALM_Completed | Wang Alex SGH CDAY52 (Z0218623) | 2026-07-23 08:37 | 2026-08-24 | 2026-08-31 | (9824551) SW-SoftwareTest PR65978 |  | 10833052, 10877111, 10798652, 10798686, 10832302, 10832336 |  |  | 2026-09-08 | Jin Bei SGH CDAY52 (JinB), Lu Shubin GNG CDAW13 (Z0155681), Liu Han SGH CDAW61 (Z0231024) | 2026-08-28 |  |  | 2 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.0561111111111111 | 937.675 | 168.181666666667 | 0 | 27.6458333333333 |  |  | Process Documents | 4 |  | 0
10867714 | work_item | 0 | ALM_Task | JAC SbW X6U SUV SWE.1 for Release OTS1_2_SW_RL2 / OTS1_2_SW_RL2_RC1 / Change 1 / Generate SW Requirements / Manage Vehicle Interface / SmtActrSourceMgrSwc | ALM_Cancelled | Khalokar Sanket HYD CDAIY2 (Z0233193) | 2026-07-20 16:44 | 2026-07-20 | 2026-07-24 | (9824545) SW-SWE-SoftwareDepartment PR65978 |  | 10861774, 10798652 |  |  |  | Luo Shengzao GNG CDAY622 (Z0097805), Liang Haijie GNG CDAW22 (Z0127635), Cai Qishu GNG CDAW22 (Z0148114), Uppala Naren EXT Agency Worker (Z0160790), Suryawanshi Naresh Kumar GNG CDAW22 (Z0167209), Wang Alex SGH CDAY52 (Z0218623), Li Changbo GNG CDAW21 (Z0290438) | 2026-07-21 |  |  |  | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.0225 | 64.3694444444444 | 0 |  |  |  |  | Requirements Analysis |  |  | 0
10860839 | work_item | 0 | ALM_Task | [SW domain implemetation task] JAC_Huawei_X2441_[ECR] Update Vehicle L4 Architecture for X6U | ALM_Completed | Liao Jiaxin SGH CDAW11 (Z0283131) | 2026-07-16 10:19 | 2026-07-16 | 2026-07-17 | (9824545) SW-SWE-SoftwareDepartment PR65978 |  | 10436107 |  |  | 2026-07-16 | Lu Shubin GNG CDAW13 (Z0155681) |  |  | 46220 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 |  | 1.52305555555556 | 0.0769444444444444 |  | 1.15416666666667 |  |  | Requirements Analysis, Process Documents | 20 |  | 0
10854586 | work_item | 0 | ALM_Task | JAC_X2441_SbW ¦ OTS2_SYS_RL2_RC1 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ System Test ¦ System Test Management ¦ System Test Summary Report | ALM_Completed | Wang Alex SGH CDAY52 (Z0218623) | 2026-07-14 08:39 | 2026-09-07 | 2026-09-10 | (9824542) MS-SYS-SystemTesting PR65978 |  | 10854585, 10833052, 10798652, 10798686, 10832302, 10832336 |  |  | 2026-09-08 | Jin Bei SGH CDAY52 (JinB), Li Jiajun GNG CDAY211 (Z0156047) | 2026-09-08 |  |  | 2 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.00777777777777778 | 1322.44472222222 | 21.7372222222222 |  | 9.11444444444444 |  |  | Process Documents | 3 |  | 0
10849388 | work_item | 0 | ALM_Task | [Sys Reqs Update] Update Small Arbitration against ECR-10798652 | ALM_Completed | Xu Huiling GNG CDAY212 (Z0129466) | 2026-07-10 11:35 | 2026-07-15 | 2026-07-31 | (9824532) AP-EPS-Systems Requirements/Design PR65978 |  | 10819509, 10798652 |  |  | 2026-08-14 | Gao Qian SGH CDAY212 (Z0131266) | 2026-07-17 | 46223 | 46224 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 837.653333333333 | 0.00555555555555555 | 0.274166666666667 |  | 0.4525 |  |  | Requirements Analysis | 16 |  | 0
10839948 | work_item | 0 | ALM_Task | JAC_X2441_SbW ¦ OTS1_SW_RL2_RC1 ¦ SWE.5&6 ¦ New and Changed Requirements ¦ Software test ¦ Software Test Management ¦ Software Test Summary Report | ALM_Completed | Wang Alex SGH CDAY52 (Z0218623) | 2026-07-07 14:36 | 2026-07-29 | 2026-08-03 | (9824551) SW-SoftwareTest PR65978 |  | 10839942, 10762747, 10798715, 10829998 |  |  | 2026-08-06 | Jin Bei SGH CDAY52 (JinB), Lu Shubin GNG CDAW13 (Z0155681), Liu Han SGH CDAW61 (Z0231024), Liao Jiaxin SGH CDAW11 (Z0283131) | 2026-07-30 |  |  | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.00666666666666667 | 547.454444444444 | 0.0288888888888889 |  | 171.376666666667 |  |  | Process Documents | 4 |  | 0
10839913 | work_item | 0 | ALM_Task | JAC_X2441_SbW ¦ OTS1_SYS_RL2_RC1&2 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ System Test ¦ System Test Management ¦ System Test Summary Report | ALM_Completed | Wang Alex SGH CDAY52 (Z0218623) | 2026-07-07 14:26 | 2026-07-29 | 2026-08-10 | (9824542) MS-SYS-SystemTesting PR65978 |  | 10839911, 10829998 |  |  | 2026-08-14 | Jin Bei SGH CDAY52 (JinB), Li Jiajun GNG CDAY211 (Z0156047) | 2026-07-31 | 46233 | 46244 | 2 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.0111111111111111 | 576.218055555556 | 24.5980555555555 | 0 | 308.141666666667 |  |  | Process Documents | 4 |  | 0
10830592 | work_item | 0 | ALM_Task | S310_Release for PV_PVM_Durability Report | ALM_Completed | Zou Dongmei SGH CDAS12 (Z0130822) | 2026-07-02 16:05 |  | 2026-07-10 | (8667841) TV-TAV-TestAndValidation PR63909 |  | 10826866, 9965134 |  |  | 2026-07-24 | Shi Xin SGH CDAS12 (ShiX2), Xie Haoting SGH CDAH212 (XieH), Xu Shun SGH CDAH24 (XuS21), He Xiaolei SGH CDAH24 (Z0190729), Geng Zhiwei SGH CDAE15 (Z0223934) |  |  |  | 1 | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 0.0213888888888889 | 0.00166666666666667 | 23.7238888888889 | 0 | 501.970277777778 |  |  | Process Documents | 8 |  | 0
10830568 | work_item | 0 | ALM_Task | S310_Release for PV_PVM_FAA Report | ALM_Completed | Zou Dongmei SGH CDAS12 (Z0130822) | 2026-07-02 15:59 |  | 2026-07-10 | (8667841) TV-TAV-TestAndValidation PR63909 |  | 10826866, 9965134 |  |  | 2026-07-23 | Shi Xin SGH CDAS12 (ShiX2), Xu Shun SGH CDAH24 (XuS21), He Xiaolei SGH CDAH24 (Z0190729), Geng Zhiwei SGH CDAE15 (Z0223934) |  |  |  | 1 | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 0.0683333333333333 | 0.00111111111111111 | 23.7336111111111 | 0 | 479.333333333333 |  |  | Process Documents | 8 |  | 0
10830539 | work_item | 0 | ALM_Task | WP_System PRN_P_SYS_RL3_2nd(GD01_GD01) | ALM_Planned | Jiang Wen EXT Alten (Z0273663) | 2026-07-02 15:46 | 2026-08-11 | 2026-09-30 | (8667826) AP-EPS-Systems Lead - LSE PR63909 |  | 10631591, 10656645, 10624439 | [8 empty] | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 1654.41305555555 | 430.204444444444 |  |  |  | 1899-12-31 |  | Process Documents
10829683 | work_item | 0 | ALM_Task | JAC SbW X6U SUV MAN.3 Software Planning / OTS1-2_SW_RL3_RC1 / Change Management / Perform Change Imapct Analysis / Change 1 / Perform Detail impact analysis / (X2441 SUV)ECRs&OPs Implement | ALM_Completed | Jiang Kaiwen SGH CDAW22 (JiangK5), Wan Yi SGH CDAW22 (WanY1), Li Li GNG CDAW22 (Z0088733), Luo Shengzao GNG CDAY622 (Z0097805), Liang Haijie GNG CDAW22 (Z0127635), Cai Qishu GNG CDAW22 (Z0148114), Uppala Naren EXT Agency Worker (Z0160790), Li Xiao SGH CDAW41 (Z0161483), Wu Xizhu GNG CDAW21 (Z0161849), Suryawanshi Naresh Kumar GNG CDAW22 (Z0167209), Yuwen Liang SGH DISC2 (Z0207084), Wang Alex SGH CDAY52 (Z0218623), Li Changbo GNG CDAW21 (Z0290438) | 2026-07-02 11:32 | 2026-07-02 | 2026-07-21 | (9824545) SW-SWE-SoftwareDepartment PR65978 |  | 10829595, 10798652, 10832336 |  | 10835251, 10810213, 10820553, 10821112, 10821388, 10822485, 10824900, 10822510, 10887652 | 2026-08-10 | Lu Shubin GNG CDAW13 (Z0155681), Liao Jiaxin SGH CDAW11 (Z0283131) | 2026-07-16 |  | 46213 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.0272222222222222 | 123.870555555556 | 816.6975 | 0 | 0.0827777777777778 |  |  | Requirements Analysis, Process Documents |  |  | 0
10829366 | work_item | 0 | ALM_Task | [SWE.3][BP4][SWE.4][BP2/4/5/6/7][HWA_S&D/FAA_S&D][SASM]/Develop SW unit verification strategy, Evaluate DD, Develop Criteria for Unit Verification, Test SW Units, Establish Traceability | ALM_Completed | Korrapati Hari Krishna HYD CDAIY2 (Z0238436) | 2026-07-02 09:33 | 2026-07-10 | 2026-07-24 | (9824587) APSW-FXX-FunctionAndControls PR65978 |  | 10829362, 10829370, 10829378, 10829385, 10798652, 10899804, 10899811, 10899822, 10899835 |  | 10820553, 10821112, 10821388, 10822485, 10824900, 10822510, 10887652 | 2026-07-23 | Khalokar Sanket HYD CDAIY2 (Z0233193) | 2026-07-17 |  | 46220 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 191.782222222222 | 240.1825 | 6.24166666666667 |  | 68.9869444444444 |  |  | Detailed Design |  |  | 0
10829364 | work_item | 0 | ALM_Task | [SWE.4][BP3/5b][HWA_S&D/FAA_S&D][SASM]/Perform Static Verification of SW Units and Establish Bidirectional Traceability | ALM_Completed | Korrapati Hari Krishna HYD CDAIY2 (Z0238436) | 2026-07-02 09:33 | 2026-07-10 | 2026-07-24 | (9824587) APSW-FXX-FunctionAndControls PR65978 |  | 10829370, 10829378, 10829385, 10798652, 10829362, 10899804, 10899811, 10899822, 10899835 |  | 10820553, 10821112, 10821388, 10822485, 10824900, 10822510, 10887652 | 2026-07-23 | Khalokar Sanket HYD CDAIY2 (Z0233193) | 2026-07-17 |  | 46227 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 191.782777777778 | 240.186111111111 | 4.11972222222222 |  | 70.9272222222222 |  |  | Detailed Design |  |  | 0
10829308 | work_item | 0 | ALM_Task | JAC SbW X6U SUV [SWE.3][BP1/2/3/5/6/7/8][HWA_S&D/FAA_S&D][SASM]/Create SW DD, Develop SW Units, Establish Traceability, Ensure Consistency, Communicate, Define interfaces, Describe dynamic behavior | ALM_Completed | Khalokar Sanket HYD CDAIY2 (Z0233193) | 2026-07-02 09:31 | 2026-07-10 | 2026-08-07 | (9824587) APSW-FXX-FunctionAndControls PR65978 |  | 10829307, 10899133, 10899188, 10899224, 10899266, 10829320, 10829333, 10829344, 10798652 |  | 10820553, 10821112, 10821388, 10822485, 10824900, 10822510, 10887652 | 2026-08-28 | Luo Shengzao GNG CDAY622 (Z0097805) | 2026-07-17 |  | 46220 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 191.811944444444 | 105.287222222222 | 1.44722222222222 | 551.315 | 526.221944444444 |  |  | Detailed Design |  |  | 0
10827208 | work_item | 0 | ALM_Task | S310_Release for PV_PVM_HWA Report | ALM_Completed | Zou Dongmei SGH CDAS12 (Z0130822) | 2026-07-01 14:48 |  | 2026-07-10 | (8667841) TV-TAV-TestAndValidation PR63909 |  | 10826866, 9965134 |  |  | 2026-07-06 | Shi Xin SGH CDAS12 (ShiX2), Xie Haoting SGH CDAH212 (XieH), Geng Zhiwei SGH CDAE15 (Z0223934) |  |  |  | 1 | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 25.1391666666667 | 0.00527777777777778 | 23.8055555555555 | 0 | 65.7336111111111 |  |  | Process Documents | 8 |  | 0
10819497 | work_item | 0 | ALM_Task | [JAC&Huawei][X2441][SbW][SYS.3][OTS2] DRBFM | ALM_Completed | Liao Kai SGH CDAY212 (Z0133157) | 2026-06-27 15:33 | 2026-07-27 | 2026-08-04 | (9824532) AP-EPS-Systems Requirements/Design PR65978 |  | 10819490, 10798652, 10798686, 10832302, 10832336, 10833052 |  |  | 2026-08-18 | Li Jiajun GNG CDAY211 (Z0156047) | 2026-07-31 | 46233 | 46238 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 811.543055555556 | 0.00194444444444444 | 0.0583333333333333 | 0 | 432.636111111111 |  |  | Architectural Design | 0 |  | 0
10819493 | work_item | 0 | ALM_Task | [JAC][X2441][SbW][SYS.1][OTS2] Stakeholder Requirements | ALM_Completed | Gu Guangyu SGH CDAY211 (Z0235949) | 2026-06-27 15:30 | 2026-07-14 | 2026-08-07 | (9824533) AP-EPS-Systems Lead - LSE PR65978 |  | 10819490, 10798652, 10832302, 10833052 |  |  | 2026-08-19 | Xiao Bowei SGH CDAY211 (Z0058246), Li Jiajun GNG CDAY211 (Z0156047) | 2026-07-17 | 46217 | 46241 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 403.548888888889 | 360.232222222222 | 365.406944444444 | 0 | 141.355555555556 |  |  | Requirements Analysis | 0 |  | 0
10819491 | work_item | 0 | ALM_Task | [JAC][X2441][SbW][SYS.1][OTS2] RMI | ALM_Completed | Gu Guangyu SGH CDAY211 (Z0235949) | 2026-06-27 15:29 | 2026-07-13 | 2026-07-31 | (9824533) AP-EPS-Systems Lead - LSE PR65978 |  | 10819490, 10798652, 10798686, 10832302, 10833052 |  |  | 2026-08-19 | Xiao Bowei SGH CDAY211 (Z0058246), Zhang Bobo SGH CDAE13 (Z0338506) | 2026-07-16 | 46216 | 46234 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 378.310555555556 | 385.025555555556 | 0.393611111111111 | 0 | 508.7825 |  |  | Requirements Analysis | 0 |  | 0
10808128 | work_item | 0 | ALM_Task | AutoX_Sbw_PPV¦SYST_Build_AutoX_SBW_P_RL3_RC3¦Sys.4-5¦New and Changed Requirements¦Test Execution¦L1_FAA ModeA/B | ALM_Completed | Xiu Zhenhong GNG CDAY55 (Z0199168) | 2026-06-23 16:00 | 2026-06-26 | 2026-07-10 | (8667835) MS-SYS-SystemTesting PR63909 |  | 10788290, 10624439 |  |  | 2026-07-31 | Xie Yilin SGH CDAY55 (Z0151165) | 2026-07-09 |  |  | 1 | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 0.00416666666666667 | 904.926388888889 | 0.194722222222222 |  | 1.7525 |  |  | Qualification Test | 60 |  | 0
10808100 | work_item | 0 | ALM_Task | AutoX_Sbw_PPV¦SYST_Build_AutoX_SBW_P_RL3_RC3¦Sys.4-5¦New and Changed Requirements¦Test Execution¦L1_FAA PUPD | ALM_Completed | Xiu Zhenhong GNG CDAY55 (Z0199168) | 2026-06-23 15:58 | 2026-06-23 | 2026-08-03 | (8667835) MS-SYS-SystemTesting PR63909 |  | 10788290, 10624439 |  |  | 2026-07-31 | Xie Yilin SGH CDAY55 (Z0151165) | 2026-07-06 |  |  | 1 | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 0.00388888888888889 | 906.511666666667 | 0.0286111111111111 |  | 0.382777777777778 |  |  | Qualification Test | 40 |  | 0
10808043 | work_item | 0 | ALM_Task | JAC_Huawei_X2441_SbW ¦ PreOTS_SYS_RL2 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ System Test ¦ System Test Management ¦ System Test Summary Report | ALM_Completed | Wang Alex SGH CDAY52 (Z0218623) | 2026-06-23 15:42 | 2026-06-29 | 2026-07-10 | (9824542) MS-SYS-SystemTesting PR65978 |  | 10808039, 10436107, 10833139, 10506032 |  |  | 2026-07-06 | Jin Bei SGH CDAY52 (JinB), Li Jiajun GNG CDAY211 (Z0156047) | 2026-07-03 | 46206 | 46213 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.00722222222222222 | 186.010833333333 | 0.401111111111111 | 0 | 119.391944444444 |  |  | Process Documents | 8 |  | 0
10807784 | work_item | 0 | ALM_Task | AutoX_Sbw_PPV¦SYST_Build_AutoX_SBW_P_RL3_RC3¦Sys.4-5¦New and Changed Requirements¦Test Execution¦L1_FAA Feature Mode Management | ALM_Completed | Xiu Zhenhong GNG CDAY55 (Z0199168) | 2026-06-23 15:05 | 2026-06-23 | 2026-07-07 | (8667835) MS-SYS-SystemTesting PR63909 |  | 10788290, 10624439 |  |  | 2026-07-31 | Xie Yilin SGH CDAY55 (Z0151165) | 2026-07-06 |  |  | 1 | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 1.21833333333333 | 815.570277777778 | 0.294444444444444 |  | 90.7225 |  |  | Qualification Test | 20 |  | 0
10807059 | work_item | 0 | ALM_Task | [JAC&Huawei][X2411][SbW][SYS.1][MPV OTS4] RMI | ALM_Completed | Gu Guangyu SGH CDAY211 (Z0235949) | 2026-06-23 09:19 | 2026-06-26 | 2026-06-30 | (9824532) AP-EPS-Systems Requirements/Design PR65978 |  | 9963700, 10629051, 10830478 |  |  | 2026-07-06 | Xiao Bowei SGH CDAY211 (Z0058246), Zheng Nan SGH CDAE13 (Z0137141) | 2026-06-29 | 46199 | 46202 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 76.4741666666667 | 0.00222222222222222 | 0.372777777777778 | 0 | 235.028888888889 |  |  | Requirements Analysis | 0 | 2026-12-31 | 0
10799943 | work_item | 0 | ALM_Task | AutoX_Sbw_PPV¦SYST_Build_AutoX_SBW_P_RL3_RC3¦Sys.4-5¦New and Changed Requirements¦Test Execution¦L1_HWA PUPD update | ALM_Completed | Xie Yilin SGH CDAY55 (Z0151165) | 2026-06-18 17:49 | 2026-06-23 | 2026-07-07 | (8667835) MS-SYS-SystemTesting PR63909 |  | 10788290, 10624439 |  |  | 2026-07-31 | Xiu Zhenhong GNG CDAY55 (Z0199168) | 2026-07-03 |  |  | 1 | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 117.043611111111 | 478.72 | 0.138888888888889 | 0 | 429.321666666667 |  |  | Qualification Test | 30 |  | 0
10798733 | work_item | 0 | ALM_Task | AutoX_Sbw_PPV¦SYST_Build_AutoX_SBW_P_RL3_RC3¦Sys.4-5¦New and Changed Requirements¦Test Execution¦L1_HWA ModeA/B | ALM_Completed | Xie Yilin SGH CDAY55 (Z0151165) | 2026-06-18 13:31 | 2026-06-23 | 2026-06-30 | (8667835) MS-SYS-SystemTesting PR63909 |  | 10788290, 10624439 |  |  | 2026-07-31 | Xiu Zhenhong GNG CDAY55 (Z0199168) | 2026-06-26 |  |  | 1 | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 0.0183333333333333 | 600.005277777778 | 0.0372222222222222 | 0 | 429.270277777778 |  |  | Qualification Test | 30 |  | 0
10798664 | work_item | 0 | ALM_Task | AutoX_Sbw_PPV¦SYST_Build_AutoX_SBW_P_RL3_RC3¦Sys.4-5¦New and Changed Requirements¦Test Execution¦L1_HWA Feature Mode Management | ALM_Completed | Xie Yilin SGH CDAY55 (Z0151165) | 2026-06-18 13:09 | 2026-06-18 | 2026-06-29 | (8667835) MS-SYS-SystemTesting PR63909 |  | 10788290, 10624439 |  |  | 2026-07-31 | Xiu Zhenhong GNG CDAY55 (Z0199168) | 2026-06-25 |  |  | 1 | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 0.125555555555555 | 600.074166666667 | 0.0680555555555556 | 0 | 429.319722222222 |  |  | Qualification Test | 50 |  | 0
10768670 | work_item | 0 | ALM_Task | JAC-Huawei SbW X6U SUV SWE.1 for Release OTS1_SW_RL2 / OTS1_SW_RL2_RC1 / Change 1 / Generate SW Requirements / Provide SbW Steering Data / ColumnFAA | ALM_Completed | B Sai Teja EXT Agency Worker (Z0311031) | 2026-06-05 16:17 | 2026-06-05 | 2026-07-03 | (9824587) APSW-FXX-FunctionAndControls PR65978 |  | 10768662, 10829998 |  |  | 2026-07-01 | Luo Shengzao GNG CDAY622 (Z0097805), Liang Haijie GNG CDAW22 (Z0127635), Cai Qishu GNG CDAW22 (Z0148114), Uppala Naren EXT Agency Worker (Z0160790), Suryawanshi Naresh Kumar GNG CDAW22 (Z0167209), Wang Alex SGH CDAY52 (Z0218623), Li Changbo GNG CDAW21 (Z0290438) | 2026-06-17 | 46188 | 46205 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.00222222222222222 | 237.338055555556 | 0.0358333333333333 | 0 | 385.143888888889 |  |  | Requirements Analysis | 5 |  | 0
10768660 | work_item | 0 | ALM_Task | JAC-Huawei SbW X6U SUV SWE.1 for Release OTS1_SW_RL2 / OTS1_SW_RL2_RC1 / Change 1 / Generate SW Requirements / Manage Electrical Lanes / LaneFitness | ALM_Completed | B Sai Teja EXT Agency Worker (Z0311031) | 2026-06-05 16:13 | 2026-06-05 | 2026-07-03 | (9824587) APSW-FXX-FunctionAndControls PR65978 |  | 10768647, 10829998 |  |  | 2026-07-01 | Luo Shengzao GNG CDAY622 (Z0097805), Liang Haijie GNG CDAW22 (Z0127635), Cai Qishu GNG CDAW22 (Z0148114), Uppala Naren EXT Agency Worker (Z0160790), Suryawanshi Naresh Kumar GNG CDAW22 (Z0167209), Wang Alex SGH CDAY52 (Z0218623), Li Changbo GNG CDAW21 (Z0290438) | 2026-06-12 | 46188 | 46205 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.00583333333333333 | 236.3625 | 0.0288888888888889 | 0 | 386.107222222222 |  |  | Requirements Analysis | 9 |  | 0
10768580 | work_item | 0 | ALM_Task | JAC-Huawei SbW X6U SUV SWE.1 for Release OTS1_SW_RL2 / OTS1_SW_RL2_RC1 / Change 1 / Generate SW Requirements / Manage System State V2 / FallbackModeManager | ALM_Completed | Karedla Krishnamurthy HYD CDAIY2 (Z0036700) | 2026-06-05 15:34 | 2026-06-05 | 2026-06-30 | (9824587) APSW-FXX-FunctionAndControls PR65978 |  | 10727220, 10829998 |  |  | 2026-06-29 | Luo Shengzao GNG CDAY622 (Z0097805), Liang Haijie GNG CDAW22 (Z0127635), Cai Qishu GNG CDAW22 (Z0148114), Uppala Naren EXT Agency Worker (Z0160790), Suryawanshi Naresh Kumar GNG CDAW22 (Z0167209), Wang Alex SGH CDAY52 (Z0218623), Li Changbo GNG CDAW21 (Z0290438) | 2026-06-15 | 46188 | 46202 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.025 | 266.772777777778 | 0.0277777777777778 | 0 | 305.711111111111 |  |  | Requirements Analysis |  |  | 0
10768560 | work_item | 0 | ALM_Task | JAC-Huawei SbW X6U SUV SWE.1 for Release OTS1_SW_RL2 / OTS1_SW_RL2_RC1 / Change 1 / Generate SW Requirements / Manage Vehicle Interface / SmtActrSourceMgrSwc | ALM_Completed | Khalokar Sanket HYD CDAIY2 (Z0233193) | 2026-06-05 15:29 | 2026-06-05 | 2026-07-03 | (9824587) APSW-FXX-FunctionAndControls PR65978 |  | 10727214, 10829998 |  |  | 2026-07-01 | Luo Shengzao GNG CDAY622 (Z0097805), Liang Haijie GNG CDAW22 (Z0127635), Cai Qishu GNG CDAW22 (Z0148114), Uppala Naren EXT Agency Worker (Z0160790), Suryawanshi Naresh Kumar GNG CDAW22 (Z0167209), Wang Alex SGH CDAY52 (Z0218623), Li Changbo GNG CDAW21 (Z0290438) | 2026-06-05 | 46198 | 46205 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.0205555555555556 | 309.634444444444 | 167.713055555556 | 0 | 143.838888888889 |  |  | Requirements Analysis |  |  | 0
10760094 | work_item | 0 | ALM_Change Request | [JAC&Huawei][X2441][SbW] System requirements monthly sprint (June Release) | ALM_Closed | Li Jiajun GNG CDAY211 (Z0156047) | 2026-06-02 18:05 |  |  | (9824533) AP-EPS-Systems Lead - LSE PR65978 | 10764633, 10764638, 10764649, 10764653, 10764664, 10807777 | 10722680, 10829998 |  |  | 2026-07-22 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.00305555555555555 | 0.000833333333333333 | 0.00111111111111111 | [5 empty] | 0 |  | 0 |  | 50 | 28 |  | Requirements |  |  | 2026-06-05 | Xu Huiling GNG CDAY212 (Z0129466), Gao Qian SGH CDAY212 (Z0131266), Liao Kai SGH CDAY212 (Z0133157), Gu Guangyu SGH CDAY211 (Z0235949)
10751244 | work_item | 0 | ALM_Task | [SWE.3][BP4][SWE.4][BP2/4/5/6/7]ColumnFAA_S&D/Develop SW unit verification strategy, Evaluate DD, Develop Criteria for Unit Verification, Test SW Units, Establish Traceability | ALM_Completed | Pendyala Nagendra HYD CDAIY2 (Z0250802) | 2026-05-28 16:45 |  | 2026-06-16 | (9824587) APSW-FXX-FunctionAndControls PR65978 |  | 10745292, 10745333, 10829998 |  |  | 2026-06-12 | B Sai Teja EXT Agency Worker (Z0311031) | 2026-06-10 |  |  | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.005 | 360.125555555556 | 0.1625 |  | 0.468055555555555 |  |  | Unit Construction, Unit Verification |  |  | 0
10751235 | work_item | 0 | ALM_Task | [SWE.4][BP3/5b]ColumnFAA_S&D/Perform Static Verification of SW Units and Establish Bidirectional Traceability | ALM_Completed | Pendyala Nagendra HYD CDAIY2 (Z0250802) | 2026-05-28 16:42 |  | 2026-06-19 | (9824587) APSW-FXX-FunctionAndControls PR65978 |  | 10745292, 10745333, 10829998 |  |  | 2026-06-12 | B Sai Teja EXT Agency Worker (Z0311031) | 2026-06-10 |  |  | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.00861111111111111 | 360.040277777778 | 0.281388888888889 |  | 0.388333333333333 |  |  | Unit Construction, Unit Verification |  |  | 0
10751229 | work_item | 0 | ALM_Task | JAC-Huawei SbW X6U SUV [SWE.3][BP1/2/3/5/6/7/8]ColumnFAA_S&D /Create SW DD, Develop SW Units, Establish Traceability, Ensure Consistency, Communicate, Define interfaces, Describe dynamic behavior | ALM_Completed | B Sai Teja EXT Agency Worker (Z0311031) | 2026-05-28 16:39 |  | 2026-06-12 | (9824587) APSW-FXX-FunctionAndControls PR65978 |  | 10727345, 10727406, 10829998 |  |  | 2026-06-25 | Luo Shengzao GNG CDAY622 (Z0097805) | 2026-06-05 |  |  | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0 | 144.746111111111 | 43.4327777777778 | 243.326944444444 | 234.428333333333 |  |  | Detailed Design | 5 |  | 0
10745267 | work_item | 0 | ALM_Task | [SWE.3][BP4][SWE.4][BP2/4/5/6/7]SASM_HWA&FAA_S&D/Develop SW unit verification strategy, Evaluate DD, Develop Criteria for Unit Verification, Test SW Units, Establish Traceability | ALM_Completed | Verma Vaishali HYD CDAIY2 (Z0172056), Repalle Srikar HYD CDAIY2 (Z0178617) | 2026-05-26 13:47 |  | 2026-06-26 | (9824587) APSW-FXX-FunctionAndControls PR65978 |  | 10745255, 10745292, 10745310, 10745333, 10829998 |  |  | 2026-06-26 | Khalokar Sanket HYD CDAIY2 (Z0233193) | 2026-06-10 |  | 46199 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.746666666666667 | 671.245277777778 | 4.35611111111111 |  | 66.1186111111111 |  |  | Process Documents |  |  | 0
10745265 | work_item | 0 | ALM_Task | [SWE.3][BP4][SWE.4][BP2/4/5/6/7]FbMM_HWA_S&D/Develop SW unit verification strategy, Evaluate DD, Develop Criteria for Unit Verification, Test SW Units, Establish Traceability | ALM_Completed | Repalle Srikar HYD CDAIY2 (Z0178617) | 2026-05-26 13:47 |  | 2026-06-12 | (9824587) APSW-FXX-FunctionAndControls PR65978 |  | 10745255, 10745310, 10829998 |  |  | 2026-06-12 | Karedla Krishnamurthy HYD CDAIY2 (Z0036700) | 2026-06-10 | 46184 | 46190 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.721111111111111 | 338.267222222222 | 0.12 |  | 69.9741666666667 |  |  | Process Documents |  |  | 0
10745263 | work_item | 0 | ALM_Task | [SWE.3][BP4][SWE.4][BP2/4/5/6/7]LaneFitness_HWA_S&D/Develop SW unit verification strategy, Evaluate DD, Develop Criteria for Unit Verification, Test SW Units, Establish Traceability | ALM_Completed | Korrapati Hari Krishna HYD CDAIY2 (Z0238436) | 2026-05-26 13:47 | 2026-06-04 | 2026-06-12 | (9824587) APSW-FXX-FunctionAndControls PR65978 |  | 10745255, 10745310, 10829998 |  |  | 2026-06-11 | B Sai Teja EXT Agency Worker (Z0311031) | 2026-06-08 | 46181 | 46183 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.688888888888889 | 239.400555555556 | 0.291388888888889 | 0 | 142.4325 |  |  | Process Documents | 0 |  | 0
10745261 | work_item | 0 | ALM_Task | [SWE.4][BP3/5b]SASM_HWA&FAA_S&D/Perform Static Verification of SW Units and Establish Bidirectional Traceability | ALM_Completed | Verma Vaishali HYD CDAIY2 (Z0172056), Repalle Srikar HYD CDAIY2 (Z0178617) | 2026-05-26 13:47 |  | 2026-06-26 | (9824587) APSW-FXX-FunctionAndControls PR65978 |  | 10745255, 10745292, 10745310, 10745333, 10829998 |  |  | 2026-06-26 | Khalokar Sanket HYD CDAIY2 (Z0233193) | 2026-06-10 |  | 46199 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.737777777777778 | 675.616111111111 | 0.0208333333333333 |  | 65.9966666666667 |  |  | Process Documents |  |  | 0
10745259 | work_item | 0 | ALM_Task | [SWE.4][BP3/5b]FbMM_HWA_S&D/Perform Static Verification of SW Units and Establish Bidirectional Traceability | ALM_Completed | Repalle Srikar HYD CDAIY2 (Z0178617) | 2026-05-26 13:47 | 2026-06-10 | 2026-06-12 | (9824587) APSW-FXX-FunctionAndControls PR65978 |  | 10745255, 10745310, 10829998 |  |  | 2026-06-11 | Karedla Krishnamurthy HYD CDAIY2 (Z0036700) | 2026-06-10 | 46183 | 46185 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.706111111111111 | 338.164444444444 | 0.113333333333333 |  | 44.5794444444444 |  |  | Process Documents |  |  | 0
10745256 | work_item | 0 | ALM_Task | [SWE.4][BP3/5b]LaneFitness_HWA_S&D/Perform Static Verification of SW Units and Establish Bidirectional Traceability | ALM_Completed | Korrapati Hari Krishna HYD CDAIY2 (Z0238436) | 2026-05-26 13:47 | 2026-06-04 | 2026-06-12 | (9824587) APSW-FXX-FunctionAndControls PR65978 |  | 10745255, 10745310, 10829998 |  |  | 2026-06-11 | B Sai Teja EXT Agency Worker (Z0311031) | 2026-06-08 | 46181 | 46183 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.674722222222222 | 239.439722222222 | 0.270277777777778 | 0 | 142.115833333333 |  |  | Process Documents | 0 |  | 0
10739988 | work_item | 0 | ALM_Change Request | JAC_Huawei_X2441_SbW ¦ PreOTS_SYS_RL2 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ system test ¦ Small Arbitration | ALM_Closed |  | 2026-05-22 14:25 |  |  | (9824542) MS-SYS-SystemTesting PR65978 | 10739996, 10740890, 10747945 | 10732077, 10436107 |  |  | 2026-07-02 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.000555555555555556 | 0.00111111111111111 | 0.000833333333333333 | [5 empty] | 0 |  | 0 |  | 149 | 128 |  | Test |  |  | 2026-05-22
10727298 | work_item | 0 | ALM_Task | JAC-Huawei SbW X6U SUV [SWE.3][BP1/2/3/5/6/7/8]SASM_HWA&FAA_S&D/Create SW DD, Develop SW Units, Establish Traceability, Ensure Consistency, Communicate, Define interfaces, Describe dynamic behavior | ALM_Completed | Khalokar Sanket HYD CDAIY2 (Z0233193) | 2026-05-18 17:20 |  | 2026-06-26 | (9824587) APSW-FXX-FunctionAndControls PR65978 |  | 10727293, 10727345, 10727383, 10727406, 10829998 |  |  | 2026-06-25 | Luo Shengzao GNG CDAY622 (Z0097805) | 2026-06-05 |  |  | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 95.6208333333333 | 357.926111111111 | 56.9016666666667 | 377.138888888889 | 17.4522222222222 |  |  | Process Documents |  |  | 0
10727296 | work_item | 0 | ALM_Task | JAC-Huawei SbW X6U SUV [SWE.3][BP1/2/3/5/6/7/8]FbMM_HWA_S&D/Create SW DD, Develop SW Units, Establish Traceability, Ensure Consistency, Communicate, Define interfaces, Describe dynamic behavior | ALM_Completed | Karedla Krishnamurthy HYD CDAIY2 (Z0036700) | 2026-05-18 17:20 | 2026-06-02 | 2026-06-12 | (9824587) APSW-FXX-FunctionAndControls PR65978 |  | 10727293, 10727383, 10829998 |  |  | 2026-06-25 | Luo Shengzao GNG CDAY622 (Z0097805) | 2026-06-05 | 46175 | 46184 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 95.6111111111111 | 291.527777777778 | 16.2019444444444 | 0 | 505.292222222222 |  |  | Process Documents |  |  | 0
10727294 | work_item | 0 | ALM_Task | JAC-Huawei SbW X6U SUV [SWE.3][BP1/2/3/5/6/7/8]Lanefitness_HWA_S&D /Create SW DD, Develop SW Units, Establish Traceability, Ensure Consistency, Communicate, Define interfaces, Describe dynamic behavior | ALM_Completed | B Sai Teja EXT Agency Worker (Z0311031) | 2026-05-18 17:20 |  | 2026-06-12 | (9824587) APSW-FXX-FunctionAndControls PR65978 |  | 10727293, 10727383, 10829998 |  |  | 2026-06-25 | Luo Shengzao GNG CDAY622 (Z0097805) | 2026-06-05 |  |  | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 95.5988888888889 | 237.885555555556 | 50.9905555555555 | 286.307777777778 | 239.430555555556 |  |  | Detailed Design, Process Documents | 18 |  | 0
10727263 | work_item | 0 | ALM_Task | JAC-Huawei SbW X6U SUV SWE.2 for Release OTS1_SW_RL2 / OTS1_SW_RL2_RC1 / FAA(S&D) / Software Architecture Formal Release | ALM_Completed | Chen Binhui SGH CDAW22 (ChenB15) | 2026-05-18 17:15 |  | 2026-06-12 | (9824585) APSW-PAC-Architecture PR65978 |  | 10727257, 10829998 |  |  | 2026-06-18 | Li Xing SGH CDAW22 (LiX39) |  |  |  | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 95.6216666666667 | 238.896388888889 | 262.524444444444 | 0 | 143.4 |  |  | Architectural Design |  |  | 0
10727258 | work_item | 0 | ALM_Task | JAC-Huawei SbW X6U SUV SWE.2 for Release OTS1_SW_RL2 / OTS1_SW_RL2_RC1 / HWA(S&D) / Software Architecture Formal Release | ALM_Completed | Liang Haijie GNG CDAW22 (Z0127635) | 2026-05-18 17:13 |  | 2026-06-23 | (9824585) APSW-PAC-Architecture PR65978 |  | 10727257, 10829998 |  |  | 2026-06-25 | Chen Binhui SGH CDAW22 (ChenB15) |  |  |  | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 95.6386111111111 | 64.6261111111111 | 720.833055555556 | 0 | 23.4211111111111 |  |  | Process Documents |  |  | 0
10727066 | work_item | 0 | ALM_Task | JAC-Huawei SbW X6U SUV MAN.3 Software Planning / OTS1_SW_RL2_RC1 / Change Management / Perform Change Imapct Analysis / Change 1 / Perform Detail impact analysis / TSC-2 Implementation | ALM_Completed | Chen Binhui SGH CDAW22 (ChenB15), Luo Shengzao GNG CDAY622 (Z0097805), Liang Haijie GNG CDAW22 (Z0127635), Cai Qishu GNG CDAW22 (Z0148114), Uppala Naren EXT Agency Worker (Z0160790), Li Xiao SGH CDAW41 (Z0161483), Wu Xizhu GNG CDAW21 (Z0161849), Suryawanshi Naresh Kumar GNG CDAW22 (Z0167209), Yuwen Liang SGH DISC2 (Z0207084), Wang Alex SGH CDAY52 (Z0218623), Li Changbo GNG CDAW21 (Z0290438) | 2026-05-18 16:59 |  | 2026-06-12 | (9824545) SW-SWE-SoftwareDepartment PR65978 |  | 10727064, 10829998 |  |  | 2026-06-22 | Lu Shubin GNG CDAW13 (Z0155681), Liao Jiaxin SGH CDAW11 (Z0283131) | 2026-06-11 |  |  | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 48.3458333333333 | 118.799166666667 | 665.145 | 0 | 0.0311111111111111 |  |  | Process Documents |  |  | 0
10720486 | work_item | 0 | ALM_Task | [SYS.2]WP_System Requirements Specification(SysRS)_ECR10624439 implementation | ALM_Cancelled | He Zhaoxia GNG CDAY212 (Z0151154) | 2026-05-14 16:08 |  | 2026-06-05 | (8667826) AP-EPS-Systems Lead - LSE PR63909 |  | 10624439 | [8 empty] | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 0 | 329.521944444444 | 0 |  |  |  |  | Requirements Analysis |  |  | 0
10713695 | work_item | 0 | ALM_Task | AUTOX HWA/FAA MAN.3 Software Planning / P_SW_RL3_RC3(S/D) / Change Management / Perform Change Imapct Analysis / Change 1 / Perform Detail impact analysis / Manage Vehicle Interface- PBI | ALM_Completed | Yang Hong SGH CDAY52 (YangH16), Lu Ming GNG CDAW21 (Z0087033), Boddeti Yasaswini HYD CDAIW4 (Z0145797), Uppu Surya Prakash EXT Agency Worker (Z0162654), Mendu Prathima HYD CDAIW2 (Z0167106), Junaid Syed Hussain BNL CDAIW2 (Z0182289), Nandigama Kalyan HYD EDEXH43 (Z0202235) | 2026-05-12 17:32 | 2026-05-12 | 2026-06-15 | (8667838) SW-SWE-SoftwareDepartment PR63909 |  | 10546373, 10624439 |  |  | 2026-06-13 | Karredla Indrasena Reddy HYD CDAIW1 (Z0288390) | 2026-05-13 | 46157 | 46188 | 1 | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP |  | 19.9766666666667 | 752.0325 | 0 | 0.323888888888889 |  |  | Requirements Analysis | 8 |  | 0
10709808 | work_item | 0 | ALM_Task | AUTOX HWA/FAA MAN.3 Software Planning / P_SW_RL3_RC3(S/D) / Change Management / Perform Change Imapct Analysis / Change 1 / Perform Detail impact analysis / Manage Vehicle Interface- VAILC | ALM_Completed | Yang Hong SGH CDAY52 (YangH16), Lu Ming GNG CDAW21 (Z0087033), Boddeti Yasaswini HYD CDAIW4 (Z0145797), Uppu Surya Prakash EXT Agency Worker (Z0162654), Mendu Prathima HYD CDAIW2 (Z0167106), Junaid Syed Hussain BNL CDAIW2 (Z0182289), Jain Neelesh HYD CDAIW3 (Z0213315) | 2026-05-11 17:25 | 2026-05-11 | 2026-06-15 | (8667838) SW-SWE-SoftwareDepartment PR63909 |  | 10546373, 10624439 |  |  | 2026-06-13 | Karredla Indrasena Reddy HYD CDAIW1 (Z0288390) | 2026-05-15 | 46157 | 46188 | 1 | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP |  | 0.180277777777778 | 795.958888888889 | 0 | 0.296111111111111 |  |  | Requirements Analysis | 16 |  | 0
10707491 | work_item | 0 | ALM_Task | [SYS.1]WP_4_RMI | ALM_Completed | Chen Xiaojian GNG CDAY211 (Z0166017) | 2026-05-09 15:07 | 2026-04-20 | 2026-05-15 | (8667826) AP-EPS-Systems Lead - LSE PR63909 |  | 10656645, 10624439 |  |  | 2026-05-15 | Xiao Bowei SGH CDAY211 (Z0058246), Jiang Wen EXT Alten (Z0273663) | 2026-05-12 | 46133 | 46157 | 1 | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 70.11 | 20.5927777777778 | 0.0513888888888889 |  | 55.5708333333333 |  |  | Requirements Analysis | 2 |  | 0
10692965 | work_item | 0 | ALM_Task | AUTOX HWA/FAA MAN.3 Software Planning / P_SW_RL3_RC3(S) / Change Management / Perform Change Imapct Analysis / Change 1 / Perform Detail impact analysis / Manage Vehicle Interface-COM and SecOC | ALM_Completed | Yang Hong SGH CDAY52 (YangH16), Lu Ming GNG CDAW21 (Z0087033), Chu Hao SGH CDAW312 (Z0091711), Boddeti Yasaswini HYD CDAIW4 (Z0145797), Uppu Surya Prakash EXT Agency Worker (Z0162654), Mendu Prathima HYD CDAIW2 (Z0167106), Junaid Syed Hussain BNL CDAIW2 (Z0182289) | 2026-05-03 21:58 | 2026-05-04 | 2026-06-15 | (8667838) SW-SWE-SoftwareDepartment PR63909 |  | 10546373, 10624439, 10656645 |  |  | 2026-06-13 | Karredla Indrasena Reddy HYD CDAIW1 (Z0288390) | 2026-05-08 | 46157 | 46188 | 1 | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 0 | 232.873888888889 | 750.7125 | 0 | 0.273611111111111 |  |  | Requirements Analysis | 27 |  | 0
10683917 | work_item | 0 | ALM_Change Request | JAC_Huawei_X2411_SbW ¦ SOP_SYS_RL4_RC1 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ system test ¦ SYS.5 ¦ Provide Vehicle Communication ¦ Test execution | ALM_Closed |  | 2026-04-28 16:05 |  |  | (9824542) MS-SYS-SystemTesting PR65978 | 10683922, 10683923, 10683930 | 10683906, 10629051 |  |  | 2026-06-18 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.000833333333333333 | 0.000833333333333333 | 0.000833333333333333 | [5 empty] | 0 |  | 0 | 10566957 | 34.6 | 40 |  | Test |  |  | 2026-04-28
10672607 | work_item | 0 | ALM_Task | SbW JAC- HWA SWE.1 for Release PP2(SOP)_SW_RL4 / PP2(SOP)_SW_RL4_RC2_S / Change 1 / Generate SW Requirements / Manage Vehicle Interface / Export EPS Data | ALM_Completed | Han Jiao SGH CDAW312 (HanJ14) | 2026-04-23 08:45 |  | 2026-06-20 | (9824545) SW-SWE-SoftwareDepartment PR65978 |  | 10672604, 10629051 |  |  | 2026-05-26 | Xiong Yuan SGH CDAW312 (Z0021652), Cai Qishu GNG CDAW22 (Z0148114), Wu Xizhu GNG CDAW21 (Z0161849), Suryawanshi Naresh Kumar GNG CDAW22 (Z0167209), Wang Alex SGH CDAY52 (Z0218623), Li Changbo GNG CDAW21 (Z0290438) |  |  |  | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 96.8038888888889 | 391.144166666667 | 24.0902777777778 | 0 | 287.723611111111 |  |  | Process Documents |  |  | 0
10663321 | work_item | 0 | ALM_Task | [SYS.1]WP_5_Analyzed customer requirement --update for ECR 10624439 & 10656645 | ALM_Completed | Chen Xiaojian GNG CDAY211 (Z0166017) | 2026-04-20 13:24 | 2026-04-20 | 2026-05-15 | (8667826) AP-EPS-Systems Lead - LSE PR63909 |  | 10656645, 10624439 |  |  | 2026-05-15 | Xiao Bowei SGH CDAY211 (Z0058246), Jiang Wen EXT Alten (Z0273663) | 2026-05-12 | 46133 | 46157 | 2 | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 217.215 | 331.209166666667 | 0.736944444444444 |  | 54.9813888888889 |  |  | Requirements Analysis | 0 |  | 0
10643329 | work_item | 0 | ALM_Task | [SYS.2]SysReq_Develop_ECR-Combine signals of decoupe/couple and HW folde status_PUPD | ALM_Completed | Z0084464, He Zhaoxia GNG CDAY212 (Z0151154) | 2026-04-10 14:53 | 2026-04-13 | 2026-05-08 | (8667825) AP-EPS-Systems Requirements/Design PR63909 |  | 10624439 |  |  | 2026-05-06 | Zhu Yongwei GNG CDAY211 (Z0138244) | 2026-04-30 |  |  | 1 | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 72.7194444444444 | 384.029166666667 | 168.273888888889 | 0 | 1.06694444444444 |  |  | Requirements Analysis | 40 |  | 0
10637699 | work_item | 0 | ALM_Task | [JAC&Huawei][X2441][SbW][SYS.1][Pre-OTS1] RMI | ALM_Completed | Gu Guangyu SGH CDAY211 (Z0235949) | 2026-04-08 15:43 | 2026-04-09 | 2026-04-15 | (9824520) AP-EPM-Engineering Project Manager PR65978 |  | 10436107, 10506032, 10818101, 10833139 |  |  | 2026-05-26 | Xiao Bowei SGH CDAY211 (Z0058246), Z0290459 | 2026-04-10 | 46121 | 46126 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 23.7486111111111 | 0.00194444444444444 | 936.080277777778 | 0 | 185.662222222222 |  |  | Requirements Analysis | 0 |  | 0
10637012 | work_item | 0 | ALM_Task | [JAC&Huawei][X2441][SbW][SYS.1][Pre-OTS1] Stakeholder Requirements | ALM_Completed | Gu Guangyu SGH CDAY211 (Z0235949) | 2026-04-08 09:59 | 2026-04-09 | 2026-04-16 | (9824532) AP-EPS-Systems Requirements/Design PR65978 |  | 10436107, 10818101, 10629051, 10833139 |  |  | 2026-05-26 | Xiao Bowei SGH CDAY211 (Z0058246), Li Jiajun GNG CDAY211 (Z0156047) | 2026-04-15 | 46121 | 46128 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 29.2625 | 0.00166666666666667 | 985.391388888889 | 0 | 136.374444444444 |  |  | Requirements Analysis | 0 |  | 0
10617043 | work_item | 0 | ALM_Task | [SYS.2]SysReq_Develop_ECR-Combine signals of decoupe/couple and HW folde status_ModeA/B | ALM_Completed | Hu Li SGH CDAY212 (HuL2) | 2026-03-30 14:10 | 2026-04-14 | 2026-05-15 | (8667825) AP-EPS-Systems Requirements/Design PR63909 |  | 10624439, 10750419 |  |  | 2026-05-28 | He Zhaoxia GNG CDAY212 (Z0151154) | 2026-05-08 |  |  | 1 | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 720.458055555556 | 338.225833333333 | 214.913055555556 | 0 | 137.828888888889 |  |  | Requirements Analysis | 150 |  | 0
10609499 | work_item | 0 | ALM_Task | [SYS.2]SysReq_Develop_ECR-Combine signals of decoupe/couple and HW folde status_FMM | ALM_Completed | Chen Ting EXT Alten (Z0099343) | 2026-03-26 09:26 | 2026-04-14 | 2026-05-08 | (8667825) AP-EPS-Systems Requirements/Design PR63909 |  | 10624439, 10701125 |  |  | 2026-05-06 | He Zhaoxia GNG CDAY212 (Z0151154) | 2026-04-30 | 46136 | 46150 | 1 | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 624.619444444444 | 199.983611111111 | 0.0241666666666667 | 0 | 165.835555555556 |  |  | Requirements Analysis | 100 |  | 0
10576191 | work_item | 0 | ALM_Task | [Sys Reqs Update] Update Small Arbitration against Vehicle L4 Architecture | ALM_Completed | Xu Huiling GNG CDAY212 (Z0129466) | 2026-03-09 15:05 | 2026-04-06 | 2026-04-20 | (9824532) AP-EPS-Systems Requirements/Design PR65978 |  | 10436107, 10722707 |  |  | 2026-05-25 | Gao Qian SGH CDAY212 (Z0131266) | 2026-04-17 | 46133 | 46169 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 1842.33777777778 | 0.005 | 0.278888888888889 |  | 3.86361111111111 |  |  | Requirements Analysis | 56 |  | 0
10570075 | work_item | 0 | ALM_Task | [JAC&Huawei][X2411][SbW][SYS.3][PP] DRBFM | ALM_Completed | Liao Kai SGH CDAY212 (Z0133157) | 2026-03-05 13:18 | 2026-03-16 | 2026-03-27 | (9824532) AP-EPS-Systems Requirements/Design PR65978 |  | 9963700, 10243178, 10350463, 10446618 |  |  | 2026-04-01 | Z0053032 | 2026-03-20 | 46101 | 46106 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 332.574444444444 | 28.2872222222222 | 0.0683333333333333 | 0 | 287.905833333333 |  |  | Requirements Analysis |  | 2026-12-31 | 0
10570063 | work_item | 0 | ALM_Task | [JAC&Huawei][X2411][SbW][MAN.3][PP] RIA | ALM_Completed | Z0053032 | 2026-03-05 13:14 | 2026-03-12 | 2026-03-20 | (9824533) AP-EPS-Systems Lead - LSE PR65978 |  | 9963700, 10243178, 10350463, 10446618 |  |  | 2026-05-06 | Huang Zhifeng SGH CDAY32 (HuangZ4), Li Yao Dr. SGH CDAY2 (LiY50), Liu Yanji SGH CDAY211 (Z0151160) | 2026-03-18 | 46099 | 46099 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 284.986111111111 | 0.00111111111111111 | 849.402777777778 | 0 | 358.728055555556 |  |  | Requirements Analysis | 2 | 2026-12-31 | 0
10546388 | work_item | 0 | ALM_Task | AUTOX HWA/FAA MAN.3 Software Planning / P_SW_RL3_RC3(S/D) / Change Management / Perform Change Imapct Analysis / Change 1 / Perform Detail impact analysis / Provide SbW External Features States- F&C OP IA | ALM_Completed | Yang Hong SGH CDAY52 (YangH16), Lu Ming GNG CDAW21 (Z0087033), Uppu Surya Prakash EXT Agency Worker (Z0162654), Guo Haiwen GNG CDAY622 (Z0163467), Mendu Prathima HYD CDAIW2 (Z0167106), Junaid Syed Hussain BNL CDAIW2 (Z0182289) | 2026-02-22 13:56 | 2026-05-11 | 2026-06-12 | (8667838) SW-SWE-SoftwareDepartment PR63909 |  | 10546383, 10624439 |  |  | 2026-06-13 | Karredla Indrasena Reddy HYD CDAIW1 (Z0288390) | 2026-05-22 | 46164 | 46171 | 1 | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 6.59416666666667 | 1795.37277777778 | 866.136944444444 | 0 | 0.0455555555555556 |  |  | Process Documents | 0 |  | 0
10546386 | work_item | 0 | ALM_Task | AUTOX HWA/FAA MAN.3 Software Planning / P_SW_RL3_RC3(S/D) / Change Management / Perform Change Imapct Analysis / Change 1 / Perform Detail impact analysis / Provide SbW External Features States-/ECR 10624439 and PUPD FMM | ALM_Completed | Yang Hong SGH CDAY52 (YangH16), Lu Ming GNG CDAW21 (Z0087033), Uppu Surya Prakash EXT Agency Worker (Z0162654), Guo Haiwen GNG CDAY622 (Z0163467), Mendu Prathima HYD CDAIW2 (Z0167106), Junaid Syed Hussain BNL CDAIW2 (Z0182289), HUANG Junjie EXT altenchina (Z0316995) | 2026-02-22 13:56 | 2026-05-11 | 2026-06-12 | (8667838) SW-SWE-SoftwareDepartment PR63909 |  | 10546383, 10624439 |  |  | 2026-06-13 | Karredla Indrasena Reddy HYD CDAIW1 (Z0288390) | 2026-05-22 | 46164 | 46171 | 1 | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 6.59444444444444 | 1796.13194444444 | 790.781666666667 | 0 | 74.5561111111111 |  |  | Process Documents | 0 |  | 0
10520078 | work_item | 0 | ALM_Task | JAC_Huawei_X2411_SbW ¦ PP_SYS_RL3_RC3 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ System Test Management ¦ System Test Summary Report | ALM_Completed | Wang Alex SGH CDAY52 (Z0218623) | 2026-02-09 14:22 | 2026-03-23 | 2026-03-30 | (9824542) MS-SYS-SystemTesting PR65978 |  | 10515408, 10350463, 10243178, 10446618 |  |  | 2026-04-27 | Jin Bei SGH CDAY52 (JinB), Z0053032 | 2026-02-25 | 46106 | 46111 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.0152777777777778 | 1702.67694444444 | 1.7825 | 0 | 139.036944444444 |  |  | Process Documents | 5 |  | 0
10512985 | work_item | 0 | ALM_Task | SbW JAC SWE.5 for Release PP_SW_RL3 / PP_SW_RL3_RC1 / Software Integration / Perform Software Bench Test / FunctionControl | ALM_Completed | Luo Shengzao GNG CDAY622 (Z0097805) | 2026-02-05 15:09 |  | 2026-02-06 | (9824587) APSW-FXX-FunctionAndControls PR65978 |  | 10428479, 10446618 |  |  | 2026-04-13 | Wu Zhuxia SGH CDAW13 (Z0171653) |  |  |  | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.005 | 1345.73472222222 | 0.0822222222222222 | 0 | 258.488333333333 |  |  | Integration Test |  |  | 0
10496999 | work_item | 0 | ALM_Task | [JAC&Huawei][X2411][SbW][SYS.1][PP]SDI Annotations_ RMI | ALM_Completed | Gu Guangyu SGH CDAY211 (Z0235949) | 2026-01-29 10:17 | 2026-01-29 | 2026-01-30 | (9824532) AP-EPS-Systems Requirements/Design PR65978 |  | 9963700, 10243178, 10446618, 10350463 |  |  | 2026-03-04 | Xiao Bowei SGH CDAY211 (Z0058246), Z0290459 | 2026-01-29 | 46052 | 46052 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 4.188333333333334 | 0.006666666666666667 | 0.1738888888888889 | 0 | 813.112222222222 |  |  | Requirements Analysis | 0 | 2026-12-31 | 0
10477476 | work_item | 0 | ALM_Task | SWE.2_Software_Arch_Design_JAC_Huawei_SbW_X2411_FAA S Lane / PP_SW_RL3 / PP_SW_RL3_RC1 / requirement trace and signal mapping / SASM | ALM_Completed | Wan Yi SGH CDAW22 (WanY1) | 2026-01-21 10:26 |  | 2026-02-27 | (9824545) SW-SWE-SoftwareDepartment PR65978 |  | 10364609, 10446618 |  |  | 2026-02-04 | Li Xing SGH CDAW22 (LiX39), Khalokar Sanket HYD CDAIY2 (Z0233193) |  |  |  | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.006944444444444444 | 222.4125 | 93.6391666666667 | 0 | 22.7697222222222 |  |  | Architectural Design |  |  | 0
10468010 | work_item | 0 | ALM_Task | [JAC&Huawei][X2411][SbW] OMM mode update as per new fault matrix | ALM_Completed | Gao Qian SGH CDAY212 (Z0131266) | 2026-01-16 13:54 | 2026-01-22 | 2026-01-29 | (9824532) AP-EPS-Systems Requirements/Design PR65978 |  | 10106931, 10467921, 10446618 |  |  | 2026-01-30 | Xu Huiling GNG CDAY212 (Z0129466) | 2026-01-23 | 46045 | 46051 | 2 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0 | 144.4088888888889 | 2.173611111111111 | 0 | 185.9725 |  |  | Requirements Analysis | 6 | 2026-12-31 | 0
10450157 | work_item | 0 | ALM_Task | SbW JAC SWE.1 for Release PP_SW_RL3 / PP_SW_RL3_RC1 / Change 1/ Generate SW Requirements / SASM | ALM_Completed | Khalokar Sanket HYD CDAIY2 (Z0233193) | 2026-01-08 09:12 |  | 2026-03-03 | (9824545) SW-SWE-SoftwareDepartment PR65978 |  | 10428361, 10446618 |  |  | 2026-03-03 | Luo Shengzao GNG CDAY622 (Z0097805), Cai Qishu GNG CDAW22 (Z0148114), Wu Xizhu GNG CDAW21 (Z0161849), Suryawanshi Naresh Kumar GNG CDAW22 (Z0167209), Wang Alex SGH CDAY52 (Z0218623) |  |  |  | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.1325 | 490.4975 | 380.461666666667 | 0 | 428.7575 |  |  | Requirements Analysis |  |  | 0
10428488 | work_item | 0 | ALM_Task | SbW JAC SWE.5 for Release PP_SW_RL3 / PP_SW_RL3_RC1 / Software Integration / Perform Software Bench Test / FunctionControl | ALM_Cancelled | Luo Shengzao GNG CDAY622 (Z0097805), Xu Qinghua SGH CDAY622 (Z0224996) | 2025-12-19 09:37 |  | 2026-01-21 | (9824545) SW-SWE-SoftwareDepartment PR65978 |  | 10446618 |  |  |  | Wu Zhuxia SGH CDAW13 (Z0171653) |  |  |  |  | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 676.0619444444444 | 481.463888888889 | 0 |  |  |  |  | Integration Test, Process Documents |  |  | 0
10428448 | work_item | 0 | ALM_Task | [SWE.3][BP4][SWE.4][BP2/4/5/6/7]SASM/Develop SW unit verification strategy, Evaluate DD, Develop Criteria for Unit Verification, Test SW Units, Establish Traceability | ALM_Completed | Verma Vaishali HYD CDAIY2 (Z0172056), Vugge Srinithya HYD CDAIY2 (Z0305085) | 2025-12-19 09:36 | 2026-01-12 | 2026-01-23 | (9824545) SW-SWE-SoftwareDepartment PR65978 |  | 10428431, 10446618 |  |  | 2026-01-22 | Khalokar Sanket HYD CDAIY2 (Z0233193) | 2026-01-22 |  | 46045 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 292.9802777777778 | 531.2472222222223 | 0.1694444444444445 |  | 3.07055555555556 |  |  | Unit Verification | 38 |  | 0
10428438 | work_item | 0 | ALM_Task | [SWE.4][BP3/5b]SASM/Perform Static Verification of SW Units and Establish Bidirectional Traceability | ALM_Completed | Verma Vaishali HYD CDAIY2 (Z0172056), Vugge Srinithya HYD CDAIY2 (Z0305085) | 2025-12-19 09:36 |  | 2026-01-23 | (9824545) SW-SWE-SoftwareDepartment PR65978 |  | 10428431, 10446618 |  |  | 2026-01-22 | Khalokar Sanket HYD CDAIY2 (Z0233193) |  |  |  | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 292.9819444444444 | 533.6644444444445 | 0.7902777777777777 |  | 0.110833333333333 |  |  | Unit Verification | 36 |  | 0
10428407 | work_item | 0 | ALM_Task | SbW JAC [SWE.3][BP1/2/3/5/6/7/8]SASM/Create SW DD, Develop SW Units, Establish Traceability, Ensure Consistency, Communicate, Define interfaces, Describe dynamic behavior | ALM_Completed | Khalokar Sanket HYD CDAIY2 (Z0233193) | 2025-12-19 09:36 |  | 2026-01-30 | (9824545) SW-SWE-SoftwareDepartment PR65978 |  | 10428400, 10428519, 10428548, 10428573, 10446618 |  |  | 2026-01-23 | Luo Shengzao GNG CDAY622 (Z0097805) |  |  |  | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 118.8272222222222 | 227.2333333333333 | 96.4475 | 380.6775 | 21.8575 |  |  | Process Documents |  |  | 0
10408352 | work_item | 0 | ALM_Change Request | BYD EM2E GenC300 CD EPS SWE.3 CID for Release SOP2_SW_RL4 / SOP2_SW_RL4_RC1(S2) / Change 1 / Perform Configurations on 3rd Party SW / CID- DIA | ALM_Closed |  | 2025-12-10 17:56 |  |  | (10128928) APSW-CPP-DiagnosticSerivce[PR60806] | 10408353, 10526313 | 10408334, 10772898 |  |  | 2026-07-02 | [5 empty] | /Steering/Projects/BYD/EM2E_CD_EPS/PR60806_ADS_APP_MY2022_BYD EM2E_EPS_CD | 0.0002777777777777778 | 0.00166666666666667 | 453.258888888889 | [5 empty] | 0 |  | 0 |  | 21 | 20 |  | Requirements
10408346 | work_item | 0 | ALM_Change Request | BYD EM2E GenC300 CD EPS SWE.3 CYS for Release SOP_SW_RL4 / SOP_SW_RL4_RC8(S2) / Change 1 / CYS updates in App SW | ALM_Closed |  | 2025-12-10 17:56 |  |  | (6418997) CDWC4_CYS_SW | 10408347, 10766178 | 10408334, 10772898 |  |  | 2026-07-02 | [5 empty] | /Steering/Projects/BYD/EM2E_CD_EPS/PR60806_ADS_APP_MY2022_BYD EM2E_EPS_CD | 0 | 0.00111111111111111 | 669.705833333333 | [5 empty] | 0 |  | 0 |  | 22 | 18 |  | Requirements
10408339 | work_item | 0 | ALM_Change Request | BYD EM2E GenC300 CD EPS SWE.3 TDM for Release SOP2_SW_RL4 / SOP2_SW_RL4_RC1(S2) / Change 1 / TDM | ALM_Closed |  | 2025-12-10 17:55 |  |  | (10088992) APSW-CPP-VehicleCommunication [PR60806] | 10408340 | 10408334, 10772898 |  |  | 2026-07-02 | [5 empty] | /Steering/Projects/BYD/EM2E_CD_EPS/PR60806_ADS_APP_MY2022_BYD EM2E_EPS_CD | 0 | 0.00111111111111111 | 527.128888888889 | [5 empty] | 0 |  | 0 |  | 1 | 9 |  | Requirements
10408335 | work_item | 0 | ALM_Change Request | BYD EM2E GenC300 CD EPS SWE.3 CID for Release SOP2_SW_RL4 / SOP2_SW_RL4_RC1(S2) / Change 1 | ALM_Closed |  | 2025-12-10 17:55 |  |  | (10088992) APSW-CPP-VehicleCommunication [PR60806] | 10408337 | 10408334, 10772898 |  |  | 2026-07-02 | [5 empty] | /Steering/Projects/BYD/EM2E_CD_EPS/PR60806_ADS_APP_MY2022_BYD EM2E_EPS_CD | 0 | 0.00333333333333333 | 501.127777777778 | [5 empty] | 0 |  | 0 |  | 35 | 30 |  | Requirements
10272597 | work_item | 0 | ALM_Task | WP_System DFBRM_PP | ALM_Completed | Ma Danrong GNG CDAY212 (Z0200250) | 2025-10-13 16:17 |  | 2026-01-27 | (8667826) AP-EPS-Systems Lead - LSE PR63909 |  | 10272508, 9965134 |  |  | 2026-02-09 | Huang He SGH CDAY2 (HuangH12), Zhu Yongwei GNG CDAY211 (Z0138244) |  |  |  | 1 | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 2422.174166666667 | 0.03166666666666667 | 0.230277777777778 | 0 | 430.443055555556 |  |  | Process Documents | 5 |  | 0
10272583 | work_item | 0 | ALM_Task | WP_Requirement Impact Analysis_PP | ALM_Completed | Zhu Yongwei GNG CDAY211 (Z0138244) | 2025-10-13 16:12 | 2025-11-18 | 2025-11-26 | (8667826) AP-EPS-Systems Lead - LSE PR63909 |  | 10272503, 9965134 |  |  | 2025-12-11 | Ma Kangle SGH CDAY32 (MaK1), Liu Yanji SGH CDAY211 (Z0151160) | 2025-11-21 | 45982 | 45987 | 1 | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | 935.0988888888888 | 0.0025 | 0.1413888888888889 | 0 | 483.688055555556 |  |  | Requirements Analysis | 4 |  | 0
9055364 | work_item | 0 | ALM_Task | [SW domain implemetation task] [ECR] [NIO NPD] New vehicle speed signals | ALM_Completed | Tian Cuicui SGH CDAW1 (Z0195922) | 2024-06-14 14:29 | 2024-06-14 | 2024-06-17 | (6522763) SW-SWE-SoftwareDepartment PR60577 |  | 8555340 |  |  | 2024-06-18 | Wang Jinqiang SGH CDAW13 (Z0131213), Wu Zhuxia SGH CDAW13 (Z0171653) | 2024-06-17 |  | 45460 | 1 | /Steering/Projects/NIO/NPD/PR60577_ADS_APP_MY2025_NIO_NPD_SbW_AP |  | 1.146944444444445 | 0.02916666666666667 | 0 | 97.83194444444445 |  |  |  | 40 | 2024-05-30 | 0
8963004 | work_item | 0 | ALM_Task | NIO NPD SbW EPS ¦ PP1_SYS_RL2 ¦ SYS.5 ¦ New and Changed Requirements Test- Test Execution¦ FAA MVI IED (FAA EB01) | ALM_Completed | Li Xinze GNG CDAW51 (Z0073991) | 2024-05-11 14:38 | 2024-05-06 | 2024-06-28 | (6522760) MS-SYS-SystemTesting PR60577 |  | 8960768, 8555340 | 8986865, 8990234, 8991015, 8992146 |  | 2024-06-21 | Deng Yipei EXT Alten (Z0146569) | 2024-05-24 | 45463 | 45471 | 1 | /Steering/Projects/NIO/NPD/PR60577_ADS_APP_MY2025_NIO_NPD_SbW_AP | 0.02916666666666667 | 0.002222222222222222 | 292.9225 | 0 | 685.7941666666667 |  |  | Integration Test, Qualification Test | 80 | 2024-05-30 | 0
8962909 | work_item | 0 | ALM_Task | NIO NPD SbW EPS ¦ PP1_SYS_RL2 ¦ SYS.5 ¦ New and Changed Requirements Test- Test Execution¦ MVI IED (HWA EB00) | ALM_Completed | Deng Yipei EXT Alten (Z0146569), Chen guanming EXT Alten (Z0165478) | 2024-05-11 13:45 | 2024-05-06 | 2024-06-28 | (6522760) MS-SYS-SystemTesting PR60577 |  | 8960768, 8555340 | 9014787, 9014894, 9014905 |  | 2024-06-20 | Li Xinze GNG CDAW51 (Z0073991) | 2024-05-24 | 45463 | 45471 | 1 | /Steering/Projects/NIO/NPD/PR60577_ADS_APP_MY2025_NIO_NPD_SbW_AP | 0.02333333333333333 | 0.0075 | 483.9147222222222 | 0 | 480.6125 |  |  | Integration Test, Qualification Test | 160 | 2024-05-30 | 0
8962576 | work_item | 0 | ALM_Task | NIO NPD SbW EPS ¦ PP1_SYS_RL2 ¦ SYS.5 ¦ New and Changed Requirements Test- Test Execution¦ MVI NIO EED (FAA EB01, HWA EB00) | ALM_Completed | Deng Yipei EXT Alten (Z0146569) | 2024-05-11 09:47 | 2024-04-29 | 2024-06-28 | (6522760) MS-SYS-SystemTesting PR60577 |  | 8960768, 8555340 |  |  | 2024-06-20 | Li Xinze GNG CDAW51 (Z0073991) | 2024-05-11 | 45463 | 45471 | 1 | /Steering/Projects/NIO/NPD/PR60577_ADS_APP_MY2025_NIO_NPD_SbW_AP | 0.0075 | 0.001388888888888889 | 53.07583333333334 | 0 | 915.3108333333333 |  |  | Integration Test, Qualification Test | 30 | 2024-05-30 | 0
8139278 | work_item | 0 | ALM_Task | WP_204_STKHReq_Sys_NIO_PP | ALM_Completed | Xie Meng EXT Alten (Z0136558) | 2023-08-27 18:15 | 2023-08-28 | 2023-11-06 | (6733864) MS-SYS-Requirement Manager |  | 8139277, 8555340, 8615196 |  |  | 2023-11-06 | Xiao Bowei SGH CDAY211 (Z0058246), Ma Zhili SGH CDAY211 (Z0059835) | 2023-11-06 | 45236 | 45236 | 1 | /Steering/Projects/NIO/NPD/PR60577_ADS_APP_MY2025_NIO_NPD_SbW_AP | 0.01861111111111111 | 1293.524722222222 | 408.2627777777778 | 0 | 0.8063888888888889 |  |  | Requirements Analysis | 100 |  | 0
10807777 | work_item | 1 | ALM_Task | [JAC&Huawei][X2441][SbW] StakeholderReview for System requirement monthly sprint (June Release) | ALM_Completed | Gao Qian SGH CDAY212 (Z0131266) | 2026-06-23 15:05 | 2026-07-13 | 2026-07-17 | (9824533) AP-EPS-Systems Lead - LSE PR65978 |  | 10760094 | 10807795, 10807803, 10807814 |  | 2026-07-21 | Hu Li SGH CDAY212 (HuL2) | 2026-07-13 | 46216 | 46220 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 475.856666666667 | 0.00138888888888889 | 0.0169444444444444 |  | 195.761388888889 |  |  | Requirements Analysis | 2 |  | 0
10766178 | work_item | 1 | ALM_Task | BYD EM2E GenC300 CD EPS SWE.3 CYS for Release SOP_SW_RL4 / SOP_SW_RL4_RC8(S2) / Change 1 / CYS updates in App SW / Secure Library checkpoint update | ALM_Completed | Patta Madhava Rao HYD CDAIW6 (Z0016755) | 2026-06-04 12:08 | 2026-06-04 | 2026-07-10 | (6418997) CDWC4_CYS_SW |  | 10408346 |  |  | 2026-07-02 | Massi Saikrishna HYD CDAIW6 (Z0000140) | 2026-07-03 | 46206 | 46213 | 1 | /Steering/Projects/BYD/EM2E_CD_EPS/PR60806_ADS_APP_MY2022_BYD EM2E_EPS_CD | 0.0122222222222222 | 33.745 | 0.0508333333333333 | 641.734166666667 | 0.1025 |  |  | Process Documents | 9 |  | 0
10764664 | work_item | 1 | ALM_Task | [Sys Reqs Update] Update Mode Management against CAN Matrix Update | ALM_Completed | Gao Qian SGH CDAY212 (Z0131266) | 2026-06-03 18:07 | 2026-06-04 | 2026-06-12 | (9824533) AP-EPS-Systems Lead - LSE PR65978 |  | 10760094 |  |  | 2026-06-11 | Hu Li SGH CDAY212 (HuL2) | 2026-06-04 | 46177 | 46185 | 2 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 16.0808333333333 | 0.00111111111111111 | 0.796944444444444 | 0 | 173.232777777778 |  |  | Requirements Analysis | 8 |  | 0
10764653 | work_item | 1 | ALM_Task | [TSC Update] 03.3_Lane Role Management | ALM_Completed | Gao Qian SGH CDAY212 (Z0131266) | 2026-06-03 18:04 | 2026-06-04 | 2026-06-12 | (9824532) AP-EPS-Systems Requirements/Design PR65978 |  | 10760094 |  |  | 2026-06-11 | Hu Li SGH CDAY212 (HuL2) | 2026-06-04 | 46177 | 46185 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 16.4027777777778 | 0.000833333333333333 | 0.00611111111111111 | 0 | 173.655555555556 |  |  | Requirements Analysis | 8 |  | 0
10764649 | work_item | 1 | ALM_Task | [TSC Update] 29_CommunicateILC | ALM_Completed | Gao Qian SGH CDAY212 (Z0131266) | 2026-06-03 18:02 | 2026-06-17 | 2026-06-22 | (9824532) AP-EPS-Systems Requirements/Design PR65978 |  | 10760094 |  |  | 2026-06-17 | Hu Li SGH CDAY212 (HuL2) | 2026-06-17 | 46190 | 46195 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 332.729722222222 | 0.00166666666666667 | 0.00777777777777778 |  | 0.300833333333333 |  |  | Requirements Analysis | 2 |  | 0
10764638 | work_item | 1 | ALM_Task | [TSC Update] 13_CommunicatePrivateBus | ALM_Completed | Gao Qian SGH CDAY212 (Z0131266) | 2026-06-03 18:00 | 2026-06-16 | 2026-06-18 | (9824532) AP-EPS-Systems Requirements/Design PR65978 |  | 10760094 |  |  | 2026-06-16 | Hu Li SGH CDAY212 (HuL2) | 2026-06-17 | 46189 | 46191 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 304.381944444444 | 0.00111111111111111 | 0.0313888888888889 |  | 2.77222222222222 |  |  | Requirements Analysis | 4 |  | 0
10764633 | work_item | 1 | ALM_Task | [TSC Update] 12_CommunicateVehicleBus | ALM_Completed | Gao Qian SGH CDAY212 (Z0131266) | 2026-06-03 17:58 | 2026-06-17 | 2026-06-18 | (9824532) AP-EPS-Systems Requirements/Design PR65978 |  | 10760094 |  |  | 2026-06-16 | Hu Li SGH CDAY212 (HuL2) | 2026-06-17 | 46190 | 46191 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 304.384444444444 | 0.00305555555555555 | 0.00944444444444444 |  | 2.88472222222222 |  |  | Requirements Analysis | 4 |  | 0
10747945 | work_item | 1 | ALM_Work Package | JAC_Huawei_X2441_SbW ¦ PreOTS_SYS_RL2 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ system test ¦ Small Arbitration ¦ Test execution | ALM_Closed |  | 2026-05-27 14:07 |  |  | (9824542) MS-SYS-SystemTesting PR65978 | 10747979, 10748051 | 10739988 |  |  | 2026-07-02 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [12 empty] | 80.6 | 48 |  | Test
10740890 | work_item | 1 | ALM_Work Package | JAC_Huawei_X2441_SbW ¦ PreOTS_SYS_RL2 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ system test ¦ Small Arbitration ¦ TC development | ALM_Closed |  | 2026-05-22 16:12 |  |  | (9824542) MS-SYS-SystemTesting PR65978 | 10740945, 10740966 | 10739988 |  |  | 2026-07-01 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [12 empty] | 46.3 | 32 |  | Test
10739996 | work_item | 1 | ALM_Work Package | JAC_Huawei_X2441_SbW ¦ PreOTS_SYS_RL2 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ System test ¦ Small Arbitration ¦ Requirement reivew | ALM_Closed |  | 2026-05-22 14:26 |  |  | (9824542) MS-SYS-SystemTesting PR65978 | 10740032, 10740047 | 10739988 |  |  | 2026-07-01 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [12 empty] | 22.1 | 48 |  | Test
10683930 | work_item | 1 | ALM_Work Package | JAC_Huawei_X2411_SbW ¦ SOP_SYS_RL4_RC4 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ system test ¦ SYS.5 ¦ Provide Vehicle Communication ¦ Test execution | ALM_Closed |  | 2026-04-28 16:09 |  |  | (9824542) MS-SYS-SystemTesting PR65978 | 10725373, 10725377 | 10683917 |  |  | 2026-06-18 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [12 empty] | 9.2 | 8 |  | Test
10683923 | work_item | 1 | ALM_Work Package | JAC_Huawei_X2411_SbW ¦ SOP_SYS_RL4_RC4 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ system test ¦ SYS.5 ¦ Provide Vehicle Communication ¦ TC development | ALM_Closed |  | 2026-04-28 16:07 |  |  | (9824542) MS-SYS-SystemTesting PR65978 | 10684057, 10684067 | 10683917 |  |  | 2026-06-18 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [12 empty] | 15.3 | 16 |  | Test
10683922 | work_item | 1 | ALM_Work Package | JAC_Huawei_X2411_SbW ¦ SOP_SYS_RL4_RC4 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ system test ¦ SYS.5 ¦ Provide Vehicle Communication ¦ Requirement review | ALM_Closed |  | 2026-04-28 16:07 |  |  | (9824542) MS-SYS-SystemTesting PR65978 | 10684033, 10684047 | 10683917 |  |  | 2026-06-18 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [12 empty] | 10.1 | 16 |  | Test
10526313 | work_item | 1 | ALM_Task | BYD EM2E GenC300 CD EPS SWE.3 CID for Release SOP2_SW_RL4 / SOP2_SW_RL4_RC1(S2) / Change 1 / Perform Configurations on 3rd Party SW / CID - DIA - Canalyzer updates | ALM_Completed | Mulam Sunanda HYD CDAIW3 (Z0216857) | 2026-02-11 11:09 | 2026-02-11 | 2026-06-26 | (10128928) APSW-CPP-DiagnosticSerivce[PR60806] |  | 10408352 |  |  | 2026-06-24 | Wang Guowei SGH CDAW32 (Z0169879) |  | 46064 | 46199 | 1 | /Steering/Projects/BYD/EM2E_CD_EPS/PR60806_ADS_APP_MY2022_BYD EM2E_EPS_CD | 0.00972222222222222 | 843.991111111111 | 1923.85 | 407.678333333333 | 22.6613888888889 |  |  | Process Documents | 4 |  | 0
10408353 | work_item | 1 | ALM_Task | BYD EM2E GenC300 CD EPS SWE.3 CID for Release SOP2_SW_RL4 / SOP2_SW_RL4_RC1(S2) / Change 1 / Perform Configurations on 3rd Party SW / CID - DIA | ALM_Completed | Mulam Sunanda HYD CDAIW3 (Z0216857) | 2025-12-10 17:56 | 2026-02-11 | 2026-06-26 | (10128928) APSW-CPP-DiagnosticSerivce[PR60806] |  | 10408352 |  |  | 2026-06-24 | Wang Guowei SGH CDAW32 (Z0169879) | 2026-06-22 | 46064 | 46199 | 1 | /Steering/Projects/BYD/EM2E_CD_EPS/PR60806_ADS_APP_MY2022_BYD EM2E_EPS_CD | 1505.16527777778 | 0.533611111111111 | 2815.21694444444 | 359.823333333333 | 22.7577777777778 |  |  | Process Documents | 16 |  | 0
10408347 | work_item | 1 | ALM_Task | BYD EM2E GenC300 CD EPS SWE.3 CYS for Release SOP_SW_RL4 / SOP_SW_RL4_RC8(S2) / Change 1 / CYS updates in App SW / CDD_XCPlock updates | ALM_Completed | Patta Madhava Rao HYD CDAIW6 (Z0016755) | 2025-12-10 17:56 | 2026-06-02 | 2026-07-03 | (6418997) CDWC4_CYS_SW |  | 10408346 |  |  | 2026-07-02 | Massi Saikrishna HYD CDAIW6 (Z0000140) | 2026-07-03 | 46206 | 46206 | 1 | /Steering/Projects/BYD/EM2E_CD_EPS/PR60806_ADS_APP_MY2022_BYD EM2E_EPS_CD | 4174.47055555555 | 78.1408333333333 | 0.0308333333333333 | 641.046111111111 | 0.0688888888888889 |  |  | Process Documents | 9 |  | 0
10408340 | work_item | 1 | ALM_Task | BYD EM2E GenC300 CD EPS SWE.3 TDM for Release SOP2_SW_RL4 / SOP2_SW_RL4_RC1(S2) / Change 1 / TDM / TDM checkpoint update | ALM_Completed | Liu Mengyang SGH CDAW312 (Z0143955) | 2025-12-10 17:56 | 2026-06-04 | 2026-06-08 | (10088992) APSW-CPP-VehicleCommunication [PR60806] |  | 10408339 |  |  | 2026-06-26 | Han Jiao SGH CDAW312 (HanJ14) | 2026-06-05 | 46177 | 46181 | 1 | /Steering/Projects/BYD/EM2E_CD_EPS/PR60806_ADS_APP_MY2022_BYD EM2E_EPS_CD | 4218.4925 | 1.48666666666667 | 0.495833333333333 | 0 | 530.7875 |  |  | Process Documents | 9 |  | 0
10408337 | work_item | 1 | ALM_Task | BYD EM2E GenC300 CD EPS SWE.3 CID for Release SOP2_SW_RL4 / SOP2_SW_RL4_RC1(S2) / Change 1 / Workout DD & Impl / CGD updates for AES128 | ALM_Completed | Kalepally L S S V Subbarao HYD CDAIW3 (Z0133284) | 2025-12-10 17:55 | 2026-02-11 | 2026-06-25 | (10088992) APSW-CPP-VehicleCommunication [PR60806] |  | 10408335 |  |  | 2026-06-25 | Mulam Sunanda HYD CDAIW3 (Z0216857) | 2026-06-24 | 46197 | 46198 | 1 | /Steering/Projects/BYD/EM2E_CD_EPS/PR60806_ADS_APP_MY2022_BYD EM2E_EPS_CD | 1505.20972222222 | 846.017777777778 | 1929.39361111111 | 425.239722222222 | 19.385 |  |  | Process Documents | 30 |  | 0
10748051 | work_item | 2 | ALM_Task | JAC_Huawei_X2441_SbW ¦ PreOTS_SYS_RL2 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ system test ¦ Small Arbitration ¦ HWA ¦ Test execution | ALM_Completed | Li Yali SGH CDAY55 (Z0190214) | 2026-05-27 14:15 | 2026-06-01 | 2026-06-30 | (9824542) MS-SYS-SystemTesting PR65978 |  | 10747945 | 10820154, 10821388, 10822485, 10822510, 10822567, 10822627, 10822631, 10820301, 10820488, 10820553, 10821112 |  | 2026-07-01 | Sun Linling SGH CDAY55 (Z0279213) | 2026-06-26 | 46199 | 46203 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.00416666666666667 | 819.117777777778 | 0.08 |  | 15.8405555555555 |  |  | Qualification Test | 24 |  | 0
10747979 | work_item | 2 | ALM_Task | JAC_Huawei_X2441_SbW ¦ PreOTS_SYS_RL2 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ system test ¦ Small Arbitration ¦ FAA ¦ Test execution | ALM_Completed | Sun Linling SGH CDAY55 (Z0279213) | 2026-05-27 14:09 | 2026-06-01 | 2026-06-30 | (9824542) MS-SYS-SystemTesting PR65978 |  | 10747945 |  |  | 2026-07-01 | Xu Xiaoxiao SGH CDAY55 (Z0128338) | 2026-06-26 | 46199 | 46203 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.00472222222222222 | 823.268055555556 | 0.126388888888889 |  | 17.6616666666667 |  |  | Qualification Test | 24 |  | 0
10740966 | work_item | 2 | ALM_Task | JAC_Huawei_X2441_SbW ¦ PreOTS_SYS_RL2 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ System test ¦ Small Arbitration ¦ HWA ¦ TC development | ALM_Completed | Li Yali SGH CDAY55 (Z0190214) | 2026-05-22 16:15 | 2026-05-29 | 2026-06-22 | (9824542) MS-SYS-SystemTesting PR65978 |  | 10740890 |  |  | 2026-07-01 | Sun Linling SGH CDAY55 (Z0279213) | 2026-06-18 | 46178 | 46185 | 2 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.00444444444444444 | 622.956111111111 | 0.610555555555555 | 0 | 328.951666666667 |  |  | Qualification Test | 16 |  | 0
10740945 | work_item | 2 | ALM_Task | JAC_Huawei_X2441_SbW ¦ PreOTS_SYS_RL2 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ System test ¦ Small Arbitration ¦ FAA ¦ TC development | ALM_Completed | Sun Linling SGH CDAY55 (Z0279213) | 2026-05-22 16:14 | 2026-05-29 | 2026-06-12 | (9824542) MS-SYS-SystemTesting PR65978 |  | 10740890 |  |  | 2026-06-30 | Xu Xiaoxiao SGH CDAY55 (Z0128338) | 2026-06-10 | 46183 | 46185 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.00388888888888889 | 932.358611111111 | 0.0191666666666667 |  | 3.62833333333333 |  |  | Qualification Test | 16 |  | 0
10740047 | work_item | 2 | ALM_Task | JAC_Huawei_X2441_SbW ¦ PreOTS_SYS_RL2 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ System test ¦ Small Arbitration ¦ HWA ¦ Requirement reivew | ALM_Completed | Li Yali SGH CDAY55 (Z0190214) | 2026-05-22 14:40 | 2026-05-22 | 2026-06-12 | (9824542) MS-SYS-SystemTesting PR65978 |  | 10739996 |  |  | 2026-06-17 | Sun Linling SGH CDAY55 (Z0279213) | 2026-06-05 | 46178 | 46185 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.005 | 430.948611111111 | 0.00833333333333333 | 0 | 187.940833333333 |  |  | Qualification Test | 24 |  | 0
10740032 | work_item | 2 | ALM_Task | JAC_Huawei_X2441_SbW ¦ PreOTS_SYS_RL2 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ System test ¦ Small Arbitration ¦ FAA ¦ Requirement reivew | ALM_Completed | Sun Linling SGH CDAY55 (Z0279213) | 2026-05-22 14:37 | 2026-05-22 | 2026-06-12 | (9824542) MS-SYS-SystemTesting PR65978 |  | 10739996 |  |  | 2026-06-13 | Xu Xiaoxiao SGH CDAY55 (Z0128338) | 2026-06-10 | 46183 | 46185 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.00916666666666666 | 454.509444444444 | 0.00916666666666666 |  | 83.8091666666667 |  |  | Qualification Test | 24 |  | 0
10725377 | work_item | 2 | ALM_Task | JAC_Huawei_X2411_SbW ¦ SOP_SYS_RL4_RC1 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ system test ¦ SYS.5 ¦ Provide Vehicle Communication ¦ HWA ¦ Test execution | ALM_Completed | Li Yali SGH CDAY55 (Z0190214) | 2026-05-18 10:57 | 2026-05-21 | 2026-06-19 | (9824542) MS-SYS-SystemTesting PR65978 |  | 10683930 |  |  | 2026-06-17 | Sun Linling SGH CDAY55 (Z0279213) | 2026-06-15 | 46188 | 46192 | 2 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.0138888888888889 | 268.188333333333 | 0.103888888888889 | 0 | 450.881666666667 |  |  | Qualification Test | 4 |  | 0
10725373 | work_item | 2 | ALM_Task | JAC_Huawei_X2411_SbW ¦ SOP_SYS_RL4_RC4 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ system test ¦ SYS.5 ¦ Provide Vehicle Communication ¦ FAA ¦ Test execution | ALM_Completed | Sun Linling SGH CDAY55 (Z0279213) | 2026-05-18 10:55 | 2026-05-21 | 2026-06-19 | (9824542) MS-SYS-SystemTesting PR65978 |  | 10683930 |  |  | 2026-06-13 | Xu Xiaoxiao SGH CDAY55 (Z0128338) | 2026-06-15 | 46188 | 46192 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.00444444444444444 | 537.8925 | 0.212222222222222 |  | 100.152777777778 |  |  | Qualification Test | 4 |  | 0
10684067 | work_item | 2 | ALM_Task | JAC_Huawei_X2411_SbW ¦ SOP_SYS_RL4_RC4 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ system test ¦ SYS.5 ¦ Provide Vehicle Communication ¦ HWA ¦ TC development | ALM_Completed | Li Yali SGH CDAY55 (Z0190214) | 2026-04-28 16:21 | 2026-05-21 | 2026-06-05 | (9824542) MS-SYS-SystemTesting PR65978 |  | 10683923 |  |  | 2026-05-29 | Sun Linling SGH CDAY55 (Z0279213) | 2026-06-03 | 46176 | 46178 | 2 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.00111111111111111 | 742.035 | 0.374444444444444 |  | 0.298333333333333 |  |  | Qualification Test | 8 |  | 0
10684057 | work_item | 2 | ALM_Task | JAC_Huawei_X2411_SbW ¦ SOP_SYS_RL4_RC4 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ system test ¦ SYS.5 ¦ Provide Vehicle Communication ¦ FAA ¦ TC development | ALM_Completed | Sun Linling SGH CDAY55 (Z0279213) | 2026-04-28 16:19 | 2026-05-21 | 2026-06-05 | (9824542) MS-SYS-SystemTesting PR65978 |  | 10683923 |  |  | 2026-06-09 | Xu Xiaoxiao SGH CDAY55 (Z0128338) | 2026-05-28 | 46170 | 46178 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.00555555555555555 | 987.026388888889 | 0.0147222222222222 |  | 19.6983333333333 |  |  | Qualification Test | 8 |  | 0
10684047 | work_item | 2 | ALM_Task | JAC_Huawei_X2411_SbW ¦ SOP_SYS_RL4_RC4 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ system test ¦ SYS.5 ¦ Provide Vehicle Communication ¦ HWA ¦ Requirement review | ALM_Completed | Li Yali SGH CDAY55 (Z0190214) | 2026-04-28 16:16 | 2026-05-21 | 2026-06-05 | (9824542) MS-SYS-SystemTesting PR65978 |  | 10683922 |  |  | 2026-06-08 | Sun Linling SGH CDAY55 (Z0279213) | 2026-06-03 | 46176 | 46178 | 2 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.00611111111111111 | 741.722777777778 | 0.353888888888889 | 0 | 246.141944444444 |  |  | Qualification Test | 8 |  | 0
10684033 | work_item | 2 | ALM_Task | JAC_Huawei_X2411_SbW ¦ SOP_SYS_RL4_RC4 ¦ SYS.4&5 ¦ New and Changed Requirements ¦ system test ¦ SYS.5 ¦ Provide Vehicle Communication ¦ FAA ¦ Requirement review | ALM_Completed | Sun Linling SGH CDAY55 (Z0279213) | 2026-04-28 16:13 | 2026-05-21 | 2026-06-05 | (9824542) MS-SYS-SystemTesting PR65978 |  | 10683922 |  |  | 2026-06-05 | Xu Xiaoxiao SGH CDAY55 (Z0128338) | 2026-05-28 | 46170 | 46178 | 1 | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | 0.00666666666666667 | 839.399166666667 | 0.00305555555555555 |  | 77.2544444444444 |  |  | Qualification Test | 8 |  | 0
10931228 | action |  | ALM_Action | [Initial IA] [MAN.3] Update Vehicle Fault Matrix | ALM_Closed | Zhang Bobo SGH CDAE13 (Z0338506) | 2026-08-25 10:14 |  |  | (9824520) AP-EPM-Engineering Project Manager PR65978 |  |  |  |  | 2026-08-31 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [10 empty] | 0 |  |  |  |  | Analysis |  | 2026-05-19 |  |  | 10829998
10931221 | action |  | ALM_Action | [Initial IA] [MAN.3] Update Debounce Time When Switching between Vehicle Control and 4th Lane Control | ALM_Closed | Zhang Bobo SGH CDAE13 (Z0338506) | 2026-08-25 10:13 |  |  | (9824520) AP-EPM-Engineering Project Manager PR65978 |  |  |  |  | 2026-08-31 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [10 empty] | 0 |  |  |  |  | Analysis |  | 2026-02-09 |  |  | 10798652
10931218 | action |  | ALM_Action | [Initial IA] [MAN.3] Add Lane1 sensor SENT signal external connection from both HWA and FAA for X6U | ALM_Closed | Zhang Bobo SGH CDAE13 (Z0338506) | 2026-08-25 10:12 |  |  | (9824520) AP-EPM-Engineering Project Manager PR65978 |  |  |  |  | 2026-08-31 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [10 empty] | 0 |  |  |  |  | Analysis |  | 2026-03-26 |  |  | 10506032
10849913 | action |  | ALM_Action | [Initial IA] [System] Update Vehicle Fault Matrix | ALM_Closed | Li Jiajun GNG CDAY211 (Z0156047) | 2026-07-10 16:09 |  |  | (9824533) AP-EPS-Systems Lead - LSE PR65978 |  |  |  |  | 2026-07-22 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [10 empty] | 0 |  |  |  |  | Analysis |  | 2026-07-15 |  |  | 10829998
10849908 | action |  | ALM_Action | [Initial IA] [SW] Update Vehicle Fault Matrix | ALM_Closed | Liao Jiaxin SGH CDAW11 (Z0283131) | 2026-07-10 16:08 |  |  | (9824590) APSW-SWPM-SWDeliveryManagent PR65978 |  |  |  |  | 2026-07-21 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [10 empty] | 0 |  |  |  |  | Analysis |  | 2026-07-21 |  |  | 10829998
10848072 | action |  | ALM_Action | [Initial IA] [System] Update Debounce Time When Switching between Vehicle Control and 4rd Lane Control | ALM_Closed | Li Jiajun GNG CDAY211 (Z0156047) | 2026-07-09 20:37 |  |  | (9824533) AP-EPS-Systems Lead - LSE PR65978 |  |  |  |  | 2026-07-22 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [10 empty] | 0 |  |  |  |  | Analysis |  | 2026-07-15 |  |  | 10798652
10848071 | action |  | ALM_Action | [Initial IA] [SW] Update Debounce Time When Switching between Vehicle Control and 4rd Lane Control | ALM_Closed | Liao Jiaxin SGH CDAW11 (Z0283131) | 2026-07-09 20:35 |  |  | (9824590) APSW-SWPM-SWDeliveryManagent PR65978 |  |  |  |  | 2026-07-21 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [10 empty] | 0 |  |  |  |  | Analysis |  | 2026-07-20 |  |  | 10798652
10639637 | action |  | ALM_Action | [Initial IA] [System] CAN Matrix update for X6M | ALM_Closed | Li Jiajun GNG CDAY211 (Z0156047) | 2026-04-09 09:55 |  |  | (9824590) APSW-SWPM-SWDeliveryManagent PR65978 |  |  |  |  | 2026-04-24 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [10 empty] | 0 |  |  |  |  | Analysis |  | 2026-04-15 |  |  | 10629051
10639636 | action |  | ALM_Action | [Initial IA] [SW] CAN Matrix update for X6M | ALM_Closed | Wu Zhuxia SGH CDAW13 (Z0171653) | 2026-04-09 09:54 |  |  | (9824590) APSW-SWPM-SWDeliveryManagent PR65978 |  |  |  |  | 2026-04-23 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [10 empty] | 0 |  |  |  |  | Analysis |  | 2026-04-14 |  |  | 10629051
10624464 | action |  | ALM_Action | [Improvement][ECR][AutoX ModelM]Changes of Mode B & FMM - Impact Analysis | ALM_Closed | Zhu Yongwei GNG CDAY211 (Z0138244) | 2026-04-01 11:39 |  |  | (8667826) AP-EPS-Systems Lead - LSE PR63909 |  |  |  |  | 2026-04-10 | [5 empty] | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | [10 empty] | 0 |  |  |  |  | Analysis |  | 2026-04-30 |  |  | 10624439
10569945 | action |  | ALM_Action | [Initial IA] [System] Add Lane1 sensor SENT signal external connection from both HWA and FAA for X6U | ALM_Closed | Li Jiajun GNG CDAY211 (Z0156047) | 2026-03-05 11:31 |  |  | (9824533) AP-EPS-Systems Lead - LSE PR65978 |  |  |  |  | 2026-03-26 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [10 empty] | 0 |  |  |  |  | Analysis |  | 2026-03-26 |  |  | 10506032
10569943 | action |  | ALM_Action | [Initial IA] [SW] Add Lane1 sensor SENT signal external connection from both HWA and FAA for X6U | ALM_Cancelled | Ran Zhenguo SGH CDAW13 (RanZ) | 2026-03-05 11:28 |  |  | (9824590) APSW-SWPM-SWDeliveryManagent PR65978 | [10 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [10 empty] | 0 |  |  |  |  | Analysis |  | 2026-03-18 |  |  | 10506032
10569939 | action |  | ALM_Action | [Initial IA] [Sensor] Add Lane1 sensor SENT signal external connection from both HWA and FAA for X6U | ALM_Closed | Tan Hong SGH CDAH5 (TanH4) | 2026-03-05 11:26 |  |  | (9824540) PD-SEN-Sensor PR65978 |  |  |  |  | 2026-03-12 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [10 empty] | 0 |  |  |  |  | Analysis |  | 2026-03-18 |  |  | 10506032
10512237 | action |  | ALM_Action | [Initial IA][System] Vehicle L4 Architecture update for X6U | ALM_Closed | Li Jiajun GNG CDAY211 (Z0156047) | 2026-02-05 10:56 |  | 2026-02-12 | (9824533) AP-EPS-Systems Lead - LSE PR65978 |  |  |  |  | 2026-03-06 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [10 empty] | 0 |  |  |  |  | Analysis |  | 2026-03-04 |  |  | 10436107
10512233 | action |  | ALM_Action | [Initial IA][SW] Vehicle L4 Architecture update for X6U | ALM_Closed | Ran Zhenguo SGH CDAW13 (RanZ) | 2026-02-05 10:54 |  | 2026-02-12 | (9824590) APSW-SWPM-SWDeliveryManagent PR65978 |  |  |  |  | 2026-03-04 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [10 empty] | 0 |  |  |  |  | Analysis |  | 2026-03-04 |  |  | 10436107
10465824 | action |  | ALM_Action | [Initial IA] [System] Update Fault Matrix | ALM_Closed | Li Jiajun GNG CDAY211 (Z0156047) | 2026-01-15 16:35 |  |  | (9824533) AP-EPS-Systems Lead - LSE PR65978 |  |  |  |  | 2026-01-22 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [10 empty] | 0 |  |  |  |  | Analysis |  | 2026-01-21 |  |  | 10446618
10465820 | action |  | ALM_Action | [Initial IA] [SW] Update Fault Matrix | ALM_Closed | Wu Zhuxia SGH CDAW13 (Z0171653) | 2026-01-15 16:33 |  |  | (9824545) SW-SWE-SoftwareDepartment PR65978 |  |  |  |  | 2026-01-22 | [5 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [10 empty] | 0 |  |  |  |  | Analysis |  | 2026-01-20 |  |  | 10446618
10418573 | action |  | ALM_Action | [Internal][ECR][AutoX ModelM] PV Mechanical change--perform system DRBFM | ALM_Cancelled | Ma Danrong GNG CDAY212 (Z0200250) | 2025-12-15 16:38 |  |  | (8667814) AP-EPM-Engineering Project Manager PR63909 | [10 empty] | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | [10 empty] | 0 |  |  |  |  | Analysis |  | 2025-12-31 |  |  | 9965134
10418545 | action |  | ALM_Action | [Internal][ECR][AutoX ModelM] PV Mechanical change---impact analysis on system | ALM_Cancelled | Zhu Yongwei GNG CDAY211 (Z0138244) | 2025-12-15 16:31 |  |  | (8667814) AP-EPM-Engineering Project Manager PR63909 | [10 empty] | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | [10 empty] | 0 |  |  |  |  | Analysis |  | 2025-12-26 |  |  | 9965134
10418539 | action |  | ALM_Action | [Internal][ECR][AutoX ModelM] PV Mechanical change--impact analysis on FAA | ALM_Closed | Xu Shun SGH CDAH24 (XuS21) | 2025-12-15 16:30 | 2025-12-29 | 2025-12-30 | (8667814) AP-EPM-Engineering Project Manager PR63909 |  |  |  |  | 2025-12-30 | [5 empty] | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | [10 empty] | 0 |  |  |  |  | Analysis |  | 2025-12-31 |  |  | 9965134
10418469 | action |  | ALM_Action | [Internal][ECR][AutoX ModelM] PV Mechanical change--- impact analysis on HWA | ALM_Closed | Xie Haoting SGH CDAH212 (XieH) | 2025-12-15 16:12 |  |  | (8667814) AP-EPM-Engineering Project Manager PR63909 |  |  |  |  | 2026-01-09 | [5 empty] | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | [10 empty] | 0 |  |  |  |  | Analysis |  | 2026-01-09 |  |  | 9965134
9047930 | action |  | ALM_Action | [SW] [Task Mgnt] Create an additional Task for SW development management and remove the other Task/CR | ALM_Closed | Tian Cuicui SGH CDAW1 (Z0195922) | 2024-06-12 14:25 | 2024-06-12 | 2024-06-14 | (6522763) SW-SWE-SoftwareDepartment PR60577 |  |  |  |  | 2024-06-14 | [5 empty] | /Steering/Projects/NIO/NPD/PR60577_ADS_APP_MY2025_NIO_NPD_SbW_AP | [8 empty] | 8 |  | 0 |  |  |  |  | Documentation |  | 2024-06-14 |  |  | 8555340
8555359 | action |  | ALM_Action | [NIO NPD] [TT RL2] [ECR] New vehicle speed signals | ALM_Closed | Wu Zhuxia SGH CDAW13 (Z0171653) | 2023-12-20 17:18 |  | 2024-03-06 | (6522763) SW-SWE-SoftwareDepartment PR60577 |  |  |  |  | 2024-02-27 | [5 empty] | /Steering/Projects/NIO/NPD/PR60577_ADS_APP_MY2025_NIO_NPD_SbW_AP | [10 empty] | 0 |  |  |  |  | Analysis |  | 2024-03-06 |  |  | 8555340
8555350 | action |  | ALM_Action | [New vehicle speed signals] Perform initial impact analysis on DBC | ALM_Closed | Xie Meng EXT Alten (Z0136558) | 2023-12-20 17:16 |  |  | (6522750) AP-EPS-Systems Requirements/Design PR60577 |  |  |  |  | 2024-04-28 | [5 empty] | /Steering/Projects/NIO/NPD/PR60577_ADS_APP_MY2025_NIO_NPD_SbW_AP | [10 empty] | 0 |  |  |  |  | Analysis |  | 2024-04-26 |  |  | 8555340
10725430 | build |  | ALM_Build | [S300]_PROTO_Delivery_JAC_Huawei_V0_CA-DDA00_[SUV_PV01] | ALM_Planned |  | 2026-05-18 11:17 |  |  | (9824520) AP-EPM-Engineering Project Manager PR65978 | 10436107, 10506032, 10762747, 10798652, 10798686, 10798715, 10829998, 10830478, 10832302, 10832336, 10833052, 10833139, 10949649 | [9 empty] | /Steering/Projects/JAC/JAC_Huawei/PR65978_SbW_JAC_Huawei_X2411 | [16 empty] | Not Applicable | 2026-09-11
10445607 | build |  | ALM_Build | System_Build_V0_BA-EEA00 | ALM_Planned |  | 2026-01-06 11:26 |  |  |  | 10431674, 10431695, 10431730, 10431873, 10624439, 10656645, 10717461, 10717506, 10717513, 10717630, 10883174, 10910060 | [9 empty] | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | [16 empty] | Not Applicable | 2026-08-30
9384136 | build |  | ALM_Build | System_Build_V0_BA_DDA00 | ALM_Planned |  | 2024-10-21 17:00 |  |  | (8667814) AP-EPM-Engineering Project Manager PR63909 | 9975599, 9977492, 9977499, 9977518, 9977545, 9977616, 9977674, 9977694, 9977744, 9978047, 9978082, 9978311, 9978445, 9978450, 9978499, 9978719, 9979099, 9979236, 9979280, 9979590, 10396850, 10399569, 10414622, 9965134, 10410426, 10426706, 10338451, 10463424, 10338461, 10463439, 10338499, 10463451, 10338502, 10463457 | [9 empty] | /Steering/Projects/AutoX/AutoX_SbW/PR63909_ADS_APP_MY2026_AutoX_SbW_AP | [16 empty] | Not Applicable | 2026-03-31
8085717 | build |  | ALM_Build | NI060577_V0_AD-DFG01 (PP Release level 2) [S300] - Release | ALM_Planned |  | 2023-08-10 23:35 |  | 2024-05-31 | (6522739) AP-EPM-Engineering Project Manager PR60577 | 8428444, 8555340, 8666510 | [9 empty] | /Steering/Projects/NIO/NPD/PR60577_ADS_APP_MY2025_NIO_NPD_SbW_AP | [5 empty] | 1902-05-02 | [10 empty] | PURL 2 | 2024-05-31
6565461 | build |  | ALM_Build | W400a_Product_Release_[BYD]_[EM2E_export]_[PV03] | ALM_Planned | Wu Zhenhua SGH CQED2 (WuZ1) | 2022-06-23 11:48 |  |  | (6418984) TV-TAV-TestAndValidation PR60806 | 6579915, 7759504, 7865796, 8340377, 8373646, 9787527, 9958568, 10772898 | [9 empty] | /Steering/Projects/BYD/EM2E_CD_EPS/PR60806_ADS_APP_MY2022_BYD EM2E_EPS_CD | [16 empty] | Not Applicable | 2022-06-29

## Edges
Parent ID | Child ID | Relation
8555340 | 8139278 | work_items
8555340 | 8962576 | work_items
8555340 | 8962909 | work_items
8555340 | 8963004 | work_items
8555340 | 9055364 | work_items
9965134 | 10272583 | work_items
9965134 | 10272597 | work_items
9965134 | 10827208 | work_items
9965134 | 10830568 | work_items
9965134 | 10830592 | work_items
10408335 | 10408337 | work_items
10408339 | 10408340 | work_items
10408346 | 10408347 | work_items
10408346 | 10766178 | work_items
10408352 | 10408353 | work_items
10408352 | 10526313 | work_items
10436107 | 10576191 | work_items
10436107 | 10637012 | work_items
10436107 | 10637699 | work_items
10436107 | 10739988 | work_items
10436107 | 10808043 | work_items
10436107 | 10860839 | work_items
10446618 | 10428407 | work_items
10446618 | 10428438 | work_items
10446618 | 10428448 | work_items
10446618 | 10428488 | work_items
10446618 | 10450157 | work_items
10446618 | 10468010 | work_items
10446618 | 10477476 | work_items
10446618 | 10496999 | work_items
10446618 | 10512985 | work_items
10446618 | 10520078 | work_items
10446618 | 10570063 | work_items
10446618 | 10570075 | work_items
10506032 | 10637699 | work_items
10506032 | 10808043 | work_items
10624439 | 10546386 | work_items
10624439 | 10546388 | work_items
10624439 | 10609499 | work_items
10624439 | 10617043 | work_items
10624439 | 10643329 | work_items
10624439 | 10663321 | work_items
10624439 | 10692965 | work_items
10624439 | 10707491 | work_items
10624439 | 10709808 | work_items
10624439 | 10713695 | work_items
10624439 | 10720486 | work_items
10624439 | 10798664 | work_items
10624439 | 10798733 | work_items
10624439 | 10799943 | work_items
10624439 | 10807784 | work_items
10624439 | 10808100 | work_items
10624439 | 10808128 | work_items
10624439 | 10830539 | work_items
10624439 | 10992974 | work_items
10624439 | 10992979 | work_items
10624439 | 10992984 | work_items
10624439 | 10992988 | work_items
10624439 | 10993028 | work_items
10624439 | 10993034 | work_items
10624439 | 10993038 | work_items
10624439 | 10993046 | work_items
10624439 | 10993048 | work_items
10624439 | 10993050 | work_items
10624439 | 10993052 | work_items
10624439 | 10993054 | work_items
10624439 | 10993057 | work_items
10629051 | 10637012 | work_items
10629051 | 10672607 | work_items
10629051 | 10683917 | work_items
10629051 | 10807059 | work_items
10683917 | 10683922 | work_items
10683917 | 10683923 | work_items
10683917 | 10683930 | work_items
10683922 | 10684033 | work_items
10683922 | 10684047 | work_items
10683923 | 10684057 | work_items
10683923 | 10684067 | work_items
10683930 | 10725373 | work_items
10683930 | 10725377 | work_items
10739988 | 10739996 | work_items
10739988 | 10740890 | work_items
10739988 | 10747945 | work_items
10739996 | 10740032 | work_items
10739996 | 10740047 | work_items
10740890 | 10740945 | work_items
10740890 | 10740966 | work_items
10747945 | 10747979 | work_items
10747945 | 10748051 | work_items
10760094 | 10764633 | work_items
10760094 | 10764638 | work_items
10760094 | 10764649 | work_items
10760094 | 10764653 | work_items
10760094 | 10764664 | work_items
10760094 | 10807777 | work_items
10772898 | 10408335 | work_items
10772898 | 10408339 | work_items
10772898 | 10408346 | work_items
10772898 | 10408352 | work_items
10798652 | 10819491 | work_items
10798652 | 10819493 | work_items
10798652 | 10819497 | work_items
10798652 | 10829308 | work_items
10798652 | 10829364 | work_items
10798652 | 10829366 | work_items
10798652 | 10829683 | work_items
10798652 | 10849388 | work_items
10798652 | 10854586 | work_items
10798652 | 10867714 | work_items
10798652 | 10874514 | work_items
10829998 | 10727066 | work_items
10829998 | 10727258 | work_items
10829998 | 10727263 | work_items
10829998 | 10727294 | work_items
10829998 | 10727296 | work_items
10829998 | 10727298 | work_items
10829998 | 10745256 | work_items
10829998 | 10745259 | work_items
10829998 | 10745261 | work_items
10829998 | 10745263 | work_items
10829998 | 10745265 | work_items
10829998 | 10745267 | work_items
10829998 | 10751229 | work_items
10829998 | 10751235 | work_items
10829998 | 10751244 | work_items
10829998 | 10760094 | work_items
10829998 | 10768560 | work_items
10829998 | 10768580 | work_items
10829998 | 10768660 | work_items
10829998 | 10768670 | work_items
10829998 | 10839913 | work_items
10829998 | 10839948 | work_items
8555340 | 8555350 | actions
8555340 | 8555359 | actions
8555340 | 9047930 | actions
9965134 | 10418469 | actions
9965134 | 10418539 | actions
9965134 | 10418545 | actions
9965134 | 10418573 | actions
10436107 | 10512233 | actions
10436107 | 10512237 | actions
10446618 | 10465820 | actions
10446618 | 10465824 | actions
10506032 | 10569939 | actions
10506032 | 10569943 | actions
10506032 | 10569945 | actions
10506032 | 10931218 | actions
10624439 | 10624464 | actions
10629051 | 10639636 | actions
10629051 | 10639637 | actions
10798652 | 10848071 | actions
10798652 | 10848072 | actions
10798652 | 10931221 | actions
10829998 | 10849908 | actions
10829998 | 10849913 | actions
10829998 | 10931228 | actions
8555340 | 8085717 | work_item_for
9965134 | 9384136 | work_item_for
10436107 | 10725430 | work_item_for
10506032 | 10725430 | work_item_for
10624439 | 10445607 | work_item_for
10772898 | 6565461 | work_item_for
10798652 | 10725430 | work_item_for
10829998 | 10725430 | work_item_for

## Metadata
Export Time | 2026-10-01 14:29
Item kind | Count
ecr | 10
work_item | 129
action | 24
build | 5
Relation | Count
work_items | 132
actions | 24
work_item_for | 8